PaNOSC WP 7 meeting - 25/03/2020

=======================================================================

Present:

-------

Rudolf (ESRF), Jean-François (ILL), Thomas (ESS), Ornela (CERIC-ERIC), Dario (CERIC-ERIC), Roberto (CERIC-ERIC), Florian (ELI), Jordi (ESRF), Andy (ESRF)

Agenda:

1. Survey tool: OpinionStage vs. others (Roberto P.)
2. D 7.1 - Photon and Neutron EOSC Stakeholder Feedback: integration of comments.
3. Feedback from other WPs.
4. Task 7.2 - Metrics and cost for the Photon and Neutron community EOSC. Discussion of the approach.
5. AOB

**Minutes:**

1. **Survey tool: OpinionStage vs. others (Roberto P.)**

This point was not discussed. It will be proposed again in next meeting.

1. **D 7.1 - Photon and Neutron EOSC Stakeholder Feedback: integration of comments.**

Most of the comments in the document were resolved. It was decided to make any changes to the text of the [document shared in google](https://docs.google.com/document/d/1gvVYIrCOXLen46-fRwVOaxfUnGgYdRR4dCjoLjCqJpE/edit?usp=sharing), within Wednesday 01/04/2020.


In particular, we expect to implement the following changes:

* add “Universities” in the description of “Users, Research Communities and Institutions” (Thomas);
* add “shareholders of RIs” in the stakeholder categories (Ornela)
* remove the table marked as possible annex 1 (Ornela)
* add all the WP 7 members as contributors of the deliverable (Ornela)
* update the last table, including the full list of stakeholders, and cancel the duplicate text in the file.
* Any other change by any partner, please do it within 01/04 or let us know that you are working on it.

1. **Feedback from other WPs.**

No feedback was received so far by WP leaders; [the file](https://docs.google.com/spreadsheets/d/1KLT3niIfvhGXsO6LcRKnJXHv9gdO-gZ6pncEJSagGWM/edit?usp=sharing) shared with google docs with the questions will be presented during next PMC meeting as a reminder.

All WP7 members are invited to contribute. To do so, please go to the third tab of the spreadsheet:



1. Task 7.2 - Metrics and cost for the Photon and Neutron community EOSC. Discussion of the approach.

There was no time for discussion. The partners will look [at the table](https://github.com/panosc-eu/panosc/blob/master/Work%20Packages/WP7%20Sustainability/Task%207.2%20Metrics%20and%20cost%20for%20the%20Photon%20and%20Neutron%20community%20EOSC/metrics%20and%20cost%20model_V2.xlsx) and modify it if necessary, or add activities.

The last version of the table to be used as the template to collect the costs is in Github, following this path: [**panosc**](https://github.com/panosc-eu/panosc)**/**[**Work Packages**](https://github.com/panosc-eu/panosc/tree/master/Work%20Packages)**/**[**WP7 Sustainability**](https://github.com/panosc-eu/panosc/tree/master/Work%20Packages/WP7%20Sustainability)**/**[**Task 7.2 Metrics and cost for the Photon and Neutron community EOSC**](https://github.com/panosc-eu/panosc/tree/master/Work%20Packages/WP7%20Sustainability/Task%207.2%20Metrics%20and%20cost%20for%20the%20Photon%20and%20Neutron%20community%20EOSC)**/metrics and cost model\_V2.xlsx**

Once the format for the collection of costs will be agreed, we will start the collection.

Next meeting will be in 2 weeks, 08.04.2020 at 11:00. The [draft agenda](https://github.com/panosc-eu/panosc/tree/master/Work%20Packages/WP7%20Sustainability/project%20meetings/2020-04-08) can be found in Github.