## Slide 1
WP6
Organisation:
  Fortnight telcos.
  Monthly public short report per task (also useful for the preparation of deliverables).
  All documents/work/discussion open per default
  All people interested could drop me a small email (perrin@ill.eu) to join the task force
  Not all partner’s contributors identified yet (recruitment process ongoing)
Current status and next actions:
6.1 Management of the Interaction with the e-Infrastructures -> EOSC Stakeholders. (M1-M48) Lead: ILL (JF.P), Contributors: ESRF (Andy)
Participation in WG (Stakeholder forum)?
Andy is currently representing PaNOSC in the EOSC6Hub strategic boards.
6.2 EOSC Hub Service Catalogue. (M1-M48) Lead: ESRF (Andy), Contributors: All (JFP, ?) + EGI
FiTSM Trainings
Identify the first service (pilot)
6.3 Data availability for the services (M1-M48). Lead: ELI (ILL may substitute to ignite the work), Contributors: all (JFP, …) + EGI + EUDAT
Evaluating FTS3
This project has received funding from the European Union's Horizon 2020 research and innovation programme under grant agreement No 823852

## Slide 2
WP6
6.4 AAI. (M1-M36) Lead: ILL (JFP), Contributors: All (?) + PaN Community (PSI, …) + GÉANT (Christos)
Work already started on specification (Bjorn/Christos/JFP)
Dedicated days in the following weeks to refine and even pilot
Report to the UmbrellaID Management team.
6.5 Services Support (M12-M48). Lead: ELI (ILL substitute to ignite the work), Contributors: all (?) + EGI
Join the EOSC-Hub service request tracking system?
Monitor what’s happening at EOSC level?
6.6 PaN Software catalogue ( M12-M36). Lead: ILL (Jamie), Contributors: all (Andy, …)
Ignite discussion on new functionalities
6.7 Data archiving pilot (M12-M48). Lead: ELI (ILL substitute to ignite the work), Contributors: ESS , EGI.eu, ILL (JFP) + STFC (Brian M.)
Identify the best protocol to transfer data (FTS3, B2SHARE, …)
Start the pilot
6.8 Procurement of commercial cloud services (M30-M42). Lead: ESRF (Rudolf)
This project has received funding from the European Union's Horizon 2020 research and innovation programme under grant agreement No 823852

## Slide 3
Task 6.5
Services Support (M12-M48). Lead: ELI (?), Contributors: all (?) + EGI (?)
Organise an integrated technical and scientific Helpdesk that will give support to data scientists (i.e scientist that would like to use the PaN open data but are not necessarily users of the facilities). This organisation should ensure that all requests are addressed following the Service Level Agreements published in the EOSC service catalogue, and that activities are aligned with the customer relationship process to be jointly defined with the support of the EOSC-hub project
Initial activities: …
This project has received funding from the European Union's Horizon 2020 research and innovation programme under grant agreement No 823852

## Slide 4
Task 6.6
PaN Software catalogue ( M12-M36). Lead: ILL (Jamie), Contributors: all (Andy, …) + EGI (?)
- Implement in the current catalogue the missing features, for instance docker/image registry link, meet the level of EOSC standard.
- In collaboration with the EOSC-hub, define and implement APIs that could allow its integration into the EOSC database catalogue. Selected software presented in the PaNData software catalogue and officially supported by at least one of the partners will benefit of this integration by being also referenced in the EOSC database catalogue.
Initial activities: …
This project has received funding from the European Union's Horizon 2020 research and innovation programme under grant agreement No 823852

## Slide 5
Task 6.7
Data archiving pilot (M12-M48). Lead: ELI, Contributors: ESS , EGI.eu, ILL (JFP) + STFC (Brian M.)
Some of the facilities do not have a long term archiving capability and need to explore solutions for archiving their data directly into EOSC. Through this activity we will get insight on the real technical requirements necessary for archiving high throughput production data over the Internet and on the suitable economical and organisational model. This task will provide a global and practical feasibility study limiting the data to be archived to 4 PB in total over 4 years.
Initial activities: …
This project has received funding from the European Union's Horizon 2020 research and innovation programme under grant agreement No 823852

## Slide 6: Task 6.8
Procurement of commercial cloud services (M30-M42). Lead: ESRF, Contributors: ESRF, ILL, XFEL.EU, ESS, ELI
Commercial cloud services may constitute an important alternative “scale-out” solution for peak demands of data analysis needs in the RIs. However, as of today the RIs do not have adequate mechanisms in place to procure and use commercial cloud services in a flexible and secure manner. This task will allow to tender commercial cloud services for all partners in a mutualised manner and acquire practical experience of how to allocate resources to individual scientists. Although initially targeted at “in-house” scientists it may at a later stage allow to enlarge the service offering of the RIs. The procurement activity will profit from experience with the e-Infrastructures, but also from the PCP procurement project HNSciCloud led by CERN. This task will require to work in close relationship with the purchasing departments of the partner RIs.

## Slide 7: Deliverables
Deliverable 6.1 EGI data-hub integration with the facilities’ data repositories (M18, R, PU, ELI)
Deliverable 6.2 Integration of local compute resources into the EOSC cloud (M12, R, PU, ELI)
Deliverable 6.3 Integration of the PaN AAI into the EOSC (M36, R,DEM, PU, ILL)
Deliverable 6.4 Demonstration of the PaN software catalogue integration into EOSC (M24, DEM, PU, ILL)
Deliverable 6.5 Report on EOSC integration (M48, R, PU, ILL). The deliverable will report on PaNOSC organizational, technical and strategic activities contributed to establish a PaNOSC data, application and services Commons. In particular, the deliverable will report on EOSC service management processes and the related performance, including incident management, data archiving and distributed computing in EOSC, and experience in cloud procurement and adoption.