## Slide 1
WP6 – EOSC integration
J-F. Perrin (ILL) 16th Jan 2019
Photon and Neutron Open Science Cloud

## Slide 2
Agenda
Introduction (myself) (10 mn)
EGI: Service catalogue, Data Availability, … (20 mn)
GÉANT: AAI (20mn)
STFC (EUDAT): Data archiving (15mn)
Discussions / next steps:
  Who (names) is engaging on tasks?
  When?
  Development/project Plan
  Relation with other WPs, need to be identified
  Risk assessment, regular review, risk owner
  How do we work? Share information? Telcos? Mailing list?
  Deliverables, how do we work?
  KPIs?
This project has received funding from the European Union's Horizon 2020 research and innovation programme under grant agreement No 823852

## Slide 3
Task 6.1
Management of the Interaction with the e-Infrastructures -> EOSC Stakeholders. (M1-M48)
Lead: ILL (Me), Contributors: ESRF (Andy)
Participation in conferences, workshops and meetings to share the needs of the community and provide information and feedback to the PaNOSC partners on the EOSC progress and more specifically on how we can efficiently integrate.
During the course of the project new questions will arise, to address them collectively we will build surveys and ensure comprehensive responses and analyses.
- Participation in the EOSC governance. Participation in WG (Stakeholder forum), strategic boards of projects like the EOSC-Hub.
This project has received funding from the European Union's Horizon 2020 research and innovation programme under grant agreement No 823852

## Slide 4
Task 6.2
EOSC Hub Service Catalogue. (M1-M48)
Lead: ESRF (Andy), Contributors: All (JFP, ?) + EGI (?)
Participate actively in the discussion for the definition of the services harmonisation. These activities include elaborating standards for service description, classification, selection of metrics/KPIs, tools for collecting these metrics and definition of appropriate service level agreements (SLAs) and monitor the respect of these SLAs.
Once the standards are defined, we will prepare accordingly the PaNOSC services for the integration into the EOSC service catalogue.
Provide for each service information and description in standardised form
Implement tools into the services allowing to collect and report standard metrics
Ensure for each services, through testing, that SLAs are met, if not, we will provide and implement action plans.
Initial activities: FiTSM Trainings ? First service (pilot) ?
This project has received funding from the European Union's Horizon 2020 research and innovation programme under grant agreement No 823852

## Slide 5
Task 6.3
Data availability for the services (M1-M48). Lead: ELI (?), Contributors: all (JFP, …) + EGI (?)
For services, where data has to be moved to computers, implement the integration of the EGI data-hub technology into the facility repositories. Test movement of data and understand the limit of such model.
For services where data are too big to be moved, we would like to test the integration of local resources into the EOSC compute cloud. We also need to evaluate security constraints and necessary measures.
In this task we will first pilot the technical solutions with one facility before rolling out to the other partners.
Initial activities: Try FTS ? How-to local resources into EOSC (security, oragnisation, Business model, …) ?
This project has received funding from the European Union's Horizon 2020 research and innovation programme under grant agreement No 823852

## Slide 6
Task 6.4
AAI. (M1-M36)
Lead: ILL (Me), Contributors: All (?) + PaN Community (PSI, …) + GÉANT
- Study the feasibility, potential impacts and sustainability of the possible models for integrating the Photon and Neutron AAI with EOSC.
- Present, discuss and reach agreement inside the Photon and Neutron facility community at large (the PaNOSC partners and other members of the AAI consortium) on the integration of the PaNOSC AAI infrastructure, delivered with GÉANT, into EOSC.
- Implement this integration at the level of the Identity providers (IdP).
- Provide solution and documentation for the integration into the different services that PaNOSC is providing.
Initial work: With Bjorn and Christos we started to discuss requirements and pilot.
This project has received funding from the European Union's Horizon 2020 research and innovation programme under grant agreement No 823852

## Slide 7
Task 6.5
Services Support (M12-M48). Lead: ELI (?), Contributors: all (?) + EGI (?)
Organise an integrated technical and scientific Helpdesk that will give support to data scientists (i.e scientist that would like to use the PaN open data but are not necessarily users of the facilities). This organisation should ensure that all requests are addressed following the Service Level Agreements published in the EOSC service catalogue, and that activities are aligned with the customer relationship process to be jointly defined with the support of the EOSC-hub project
Initial activities: …
This project has received funding from the European Union's Horizon 2020 research and innovation programme under grant agreement No 823852

## Slide 8
Task 6.6
PaN Software catalogue ( M12-M36). Lead: ILL (Jamie), Contributors: all (Andy, …) + EGI (?)
- Implement in the current catalogue the missing features, for instance docker/image registry link, meet the level of EOSC standard.
- In collaboration with the EOSC-hub, define and implement APIs that could allow its integration into the EOSC database catalogue. Selected software presented in the PaNData software catalogue and officially supported by at least one of the partners will benefit of this integration by being also referenced in the EOSC database catalogue.
Initial activities: …
This project has received funding from the European Union's Horizon 2020 research and innovation programme under grant agreement No 823852

## Slide 9
Task 6.7
Data archiving pilot (M12-M48). Lead: ELI, Contributors: ESS , EGI.eu, ILL (JFP) + STFC (Brian M.)
Some of the facilities do not have a long term archiving capability and need to explore solutions for archiving their data directly into EOSC. Through this activity we will get insight on the real technical requirements necessary for archiving high throughput production data over the Internet and on the suitable economical and organisational model. This task will provide a global and practical feasibility study limiting the data to be archived to 4 PB in total over 4 years.
Initial activities: …
This project has received funding from the European Union's Horizon 2020 research and innovation programme under grant agreement No 823852

## Slide 10: Task 6.8
Procurement of commercial cloud services (M30-M42). Lead: ESRF, Contributors: ESRF, ILL, XFEL.EU, ESS, ELI
Commercial cloud services may constitute an important alternative “scale-out” solution for peak demands of data analysis needs in the RIs. However, as of today the RIs do not have adequate mechanisms in place to procure and use commercial cloud services in a flexible and secure manner. This task will allow to tender commercial cloud services for all partners in a mutualised manner and acquire practical experience of how to allocate resources to individual scientists. Although initially targeted at “in-house” scientists it may at a later stage allow to enlarge the service offering of the RIs. The procurement activity will profit from experience with the e-Infrastructures, but also from the PCP procurement project HNSciCloud led by CERN. This task will require to work in close relationship with the purchasing departments of the partner RIs.

## Slide 11: Deliverables
Deliverable 6.1 EGI data-hub integration with the facilities’ data repositories (M18, R, PU, ELI)
Deliverable 6.2 Integration of local compute resources into the EOSC cloud (M12, R, PU, ELI)
Deliverable 6.3 Integration of the PaN AAI into the EOSC (M36, R,DEM, PU, ILL)
Deliverable 6.4 Demonstration of the PaN software catalogue integration into EOSC (M24, DEM, PU, ILL)
Deliverable 6.5 Report on EOSC integration (M48, R, PU, ILL). The deliverable will report on PaNOSC organizational, technical and strategic activities contributed to establish a PaNOSC data, application and services Commons. In particular, the deliverable will report on EOSC service management processes and the related performance, including incident management, data archiving and distributed computing in EOSC, and experience in cloud procurement and adoption.