## PaNOSC Expenses
WP | Category | All Partners so far |  |  |  | ESRF |  |  |  | ILL |  |  |  | XFEL |  |  |  | ESS |  |  |  | ELI |  |  |  | CERIC |  |  |  | EGI
|  | 12 | 24 | 36 | TOTAL | 12 | 24 | 36 | 48 | 12 | 24 | 36 | 48 | 12 | 24 | 36 | 48 | 12 | 24 | 36 | 48 | 12 | 24 | 36 | 48 | 12 | 24 | 36 | 48 | 12 | 24 | 36 | 48
WP1 MANAGEMENT | Target PMs | 17.5 | 33 | 48.5 | 64 | 13.75 | 25.5 | 37.25 | 49 | 0.75 | 1.5 | 2.25 | 3 | 0.75 | 1.5 | 2.25 | 3 | 0.75 | 1.5 | 2.25 | 3 | 0.75 | 1.5 | 2.25 | 3 | 0.75 | 1.5 | 2.25 | 3 | 0 | 0 | 0 | 0
| Target Cost (K€) | 121.8958 | 229.625 | 337.3542 | 445.0833 | 97.3958 | 180.625 | 263.8542 | 347.0833 | 5.4375 | 10.875 | 16.3125 | 21.75 | 6 | 12 | 18 | 24 | 6.1875 | 12.375 | 18.5625 | 24.75 | 3.4688 | 6.9375 | 10.4062 | 13.875 | 3.4062 | 6.8125 | 10.2188 | 13.625 | 0 | 0 | 0 | 0
Actual PMs
Actual Cost (K€)
| Forecasted Cost (K€) |  |  |  |  | 0 | 0 | 0 | 0
| Target Travel (K€) | 49.8438 | 99.6875 | 149.5312 | 199.375 | 4.6063 | 9.2125 | 13.8187 | 18.425 | 4.6063 | 9.2125 | 13.8187 | 18.425 | 4.6063 | 9.2125 | 13.8187 | 18.425 | 4.6063 | 9.2125 | 13.8187 | 18.425 | 13.4062 | 26.8125 | 40.2188 | 53.625 | 13.4062 | 26.8125 | 40.2188 | 53.625 | 4.6063 | 9.2125 | 13.8187 | 18.425
| Actual Travel (K€) |  |  |  |  | 0
| Target Purchases (K€) | 17.2 | 34.4 | 51.6 | 68.8 | 3.825 | 7.65 | 11.475 | 15.3 | 1.375 | 2.75 | 4.125 | 5.5 | 3.25 | 6.5 | 9.75 | 13 | 3.5 | 7 | 10.5 | 14 | 2.25 | 4.5 | 6.75 | 9 | 2.25 | 4.5 | 6.75 | 9 | 0.75 | 1.5 | 2.25 | 3
| Actual Purchases (K€) |  |  |  |  | 0
| Total Target (K€) | 188.9396 | 363.7125 | 538.4854 | 713.2583 | 105.8271 | 197.4875 | 289.1479 | 380.8083 | 11.4187 | 22.8375 | 34.2563 | 45.675 | 13.8562 | 27.7125 | 41.5688 | 55.425 | 14.2937 | 28.5875 | 42.8813 | 57.175 | 19.125 | 38.25 | 57.375 | 76.5 | 19.0625 | 38.125 | 57.1875 | 76.25 | 5.3563 | 10.7125 | 16.0688 | 21.425
| Total Actual (K€) |  |  |  |  | 0
Difference (K€)
WP2 DATA POLICY | Target PMs | 23.222 | 56.4571 | 76 | 76 | 6.8798 | 14.6514 | 17 | 17 | 2.4213 | 6.6914 | 10 | 10 | 1.1813 | 2.5714 | 3 | 3 | 4.4598 | 10.6914 | 14 | 14 | 4.2556 | 13.1086 | 20 | 20 | 4.0242 | 8.7429 | 12 | 12 | 0 | 0 | 0 | 0
| Target Cost (K€) | 150.4887 | 361.4038 | 479.4167 | 479.4167 | 48.7318 | 103.781 | 120.4167 | 120.4167 | 17.5546 | 48.5129 | 72.5 | 72.5 | 9.4505 | 20.5714 | 24 | 24 | 36.7932 | 88.2043 | 115.5 | 115.5 | 19.6822 | 60.6271 | 92.5 | 92.5 | 18.2765 | 39.7071 | 54.5 | 54.5 | 0 | 0 | 0 | 0
Actual PMs
Actual Cost (K€)
Forecasted Cost (K€)
| Target Travel (K€) | 4.785 | 9.57 | 14.355 | 19.14 | 0.7975 | 1.595 | 2.3925 | 3.19 | 0.7975 | 1.595 | 2.3925 | 3.19 | 0.7975 | 1.595 | 2.3925 | 3.19 | 0.7975 | 1.595 | 2.3925 | 3.19 | 0.7975 | 1.595 | 2.3925 | 3.19 | 0.7975 | 1.595 | 2.3925 | 3.19 | 0 | 0 | 0 | 0
Actual Travel (K€)
| Target Purchases (K€) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Actual Purchases (K€) |  |  |  |  | 0
| Total Target (K€) | 155.2737 | 370.9738 | 493.7717 | 498.5567 | 49.5293 | 105.376 | 122.8092 | 123.6067 | 18.3521 | 50.1079 | 74.8925 | 75.69 | 10.248 | 22.1664 | 26.3925 | 27.19 | 37.5907 | 89.7993 | 117.8925 | 118.69 | 20.4797 | 62.2221 | 94.8925 | 95.69 | 19.074 | 41.3021 | 56.8925 | 57.69 | 0 | 0 | 0 | 0
Total Actual (K€)
Difference (K€)
WP3 DATA CATALOG | Target PMs | 62.3784 | 167.1189 | 241.0823 | 291 | 2.4672 | 9.7019 | 18.331 | 25 | 5.8681 | 13.6286 | 18.6514 | 21 | 7.8764 | 18.7367 | 29.5626 | 36 | 13.7033 | 30.9143 | 39.3657 | 43 | 19.3757 | 50.5127 | 67.0221 | 78 | 13.0876 | 43.6247 | 68.1495 | 88 | 0 | 0 | 0 | 0
| Target Cost (K€) | 385.1358 | 1004.2158 | 1445.8248 | 1732.5 | 17.4759 | 68.722 | 129.8443 | 177.0833 | 42.544 | 98.8071 | 135.2229 | 152.25 | 63.0116 | 149.8934 | 236.501 | 288 | 113.0522 | 255.0429 | 324.7671 | 354.75 | 89.6126 | 233.6214 | 309.9771 | 360.75 | 59.4396 | 198.1289 | 309.5123 | 399.6667 | 0 | 0 | 0 | 0
Actual PMs
Actual Cost (K€)
Forecasted Cost (K€)
| Target Travel (K€) | 4.785 | 9.57 | 14.355 | 19.14 | 0.7975 | 1.595 | 2.3925 | 3.19 | 0.7975 | 1.595 | 2.3925 | 3.19 | 0.7975 | 1.595 | 2.3925 | 3.19 | 0.7975 | 1.595 | 2.3925 | 3.19 | 0.7975 | 1.595 | 2.3925 | 3.19 | 0.7975 | 1.595 | 2.3925 | 3.19 | 0 | 0 | 0 | 0
Actual Travel (K€)
| Target Purchases (K€) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Actual Purchases (K€) |  |  |  |  | 0
| Total Target (K€) | 389.9208 | 1013.7858 | 1460.1798 | 1751.64 | 18.2734 | 70.317 | 132.2368 | 180.2733 | 43.3415 | 100.4021 | 137.6154 | 155.44 | 63.8091 | 151.4884 | 238.8935 | 291.19 | 113.8497 | 256.6379 | 327.1596 | 357.94 | 90.4101 | 235.2164 | 312.3696 | 363.94 | 60.2371 | 199.7239 | 311.9048 | 402.8567 | 0 | 0 | 0 | 0
Total Actual (K€)
Difference (K€)
WP4 DATA ANALYSIS | Target PMs | 62 | 148 | 234 | 309 | 6.5 | 16 | 25.5 | 36 | 18 | 39 | 60 | 71 | 12.5 | 27.6667 | 42.8333 | 60 | 6.5 | 16 | 25.5 | 32 | 8.5 | 22 | 35.5 | 50 | 10 | 27.3333 | 44.6667 | 60 | 0 | 0 | 0 | 0
| Target Cost (K€) | 414.8958 | 975.3056 | 1535.7153 | 2017.5 | 46.0417 | 113.3333 | 180.625 | 255 | 130.5 | 282.75 | 435 | 514.75 | 100 | 221.3333 | 342.6667 | 480 | 53.625 | 132 | 210.375 | 264 | 39.3125 | 101.75 | 164.1875 | 231.25 | 45.4167 | 124.1389 | 202.8611 | 272.5 | 0 | 0 | 0 | 0
Actual PMs
Actual Cost (K€)
Forecasted Cost (K€)
| Target Travel (K€) | 15.07 | 30.14 | 45.21 | 60.28 | 1.595 | 3.19 | 4.785 | 6.38 | 1.595 | 3.19 | 4.785 | 6.38 | 7.095 | 14.19 | 21.285 | 28.38 | 1.595 | 3.19 | 4.785 | 6.38 | 1.595 | 3.19 | 4.785 | 6.38 | 1.595 | 3.19 | 4.785 | 6.38 | 0 | 0 | 0 | 0
Actual Travel (K€)
| Target Purchases (K€) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Actual Purchases (K€) |  |  |  |  | 0
| Total Target (K€) | 429.9658 | 1005.4456 | 1580.9253 | 2077.78 | 47.6367 | 116.5233 | 185.41 | 261.38 | 132.095 | 285.94 | 439.785 | 521.13 | 107.095 | 235.5233 | 363.9517 | 508.38 | 55.22 | 135.19 | 215.16 | 270.38 | 40.9075 | 104.94 | 168.9725 | 237.63 | 47.0117 | 127.3289 | 207.6461 | 278.88 | 0 | 0 | 0 | 0
Total Actual (K€)
Difference (K€)
WP5 VINYL | Target PMs | 29 | 84 | 145.5 | 219 | 11 | 25 | 29 | 40 | 0 | 6 | 18 | 36 | 7 | 18 | 32 | 48 | 1 | 7 | 19.5 | 31 | 4.5 | 9 | 16.5 | 24 | 5.5 | 19 | 30.5 | 40 | 0 | 0 | 0 | 0
| Target Cost (K€) | 187.9583 | 550.25 | 967.625 | 1476.75 | 77.9167 | 177.0833 | 205.4167 | 283.3333 | 0 | 43.5 | 130.5 | 261 | 56 | 144 | 256 | 384 | 8.25 | 57.75 | 160.875 | 255.75 | 20.8125 | 41.625 | 76.3125 | 111 | 24.9792 | 86.2917 | 138.5208 | 181.6667 | 0 | 0 | 0 | 0
Actual PMs
Actual Cost (K€)
Forecasted Cost (K€)
| Target Travel (K€) | 4.785 | 9.57 | 14.355 | 19.14 | 0.7975 | 1.595 | 2.3925 | 3.19 | 0.7975 | 1.595 | 2.3925 | 3.19 | 0.7975 | 1.595 | 2.3925 | 3.19 | 0.7975 | 1.595 | 2.3925 | 3.19 | 0.7975 | 1.595 | 2.3925 | 3.19 | 0.7975 | 1.595 | 2.3925 | 3.19 | 0 | 0 | 0 | 0
Actual Travel (K€)
| Target Purchases (K€) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Actual Purchases (K€) |  |  |  |  | 0
| Total Target (K€) | 192.7433 | 559.82 | 981.98 | 1495.89 | 78.7142 | 178.6783 | 207.8092 | 286.5233 | 0.7975 | 45.095 | 132.8925 | 264.19 | 56.7975 | 145.595 | 258.3925 | 387.19 | 9.0475 | 59.345 | 163.2675 | 258.94 | 21.61 | 43.22 | 78.705 | 114.19 | 25.7767 | 87.8867 | 140.9133 | 184.8567 | 0 | 0 | 0 | 0
Total Actual (K€)
Difference (K€)
WP6 EOSC Integration | Target PMs | 38.3923 | 93.9326 | 150.0114 | 192 | 3.4348 | 9.8187 | 16.7412 | 21 | 6.3922 | 19.8481 | 33.3041 | 38 | 2.0788 | 5.9414 | 9.8041 | 13 | 2.0788 | 5.9414 | 9.8041 | 13 | 1.8288 | 5.4414 | 9.0541 | 12 | 2.0788 | 5.9414 | 9.8041 | 13 | 20.5 | 41 | 61.5 | 82
| Target Cost (K€) | 243.978 | 605.3963 | 970.6288 | 1236.5397 | 24.3297 | 69.5494 | 118.5832 | 148.75 | 46.3432 | 143.8988 | 241.4544 | 275.5 | 16.6306 | 47.5315 | 78.4324 | 104 | 17.1503 | 49.0169 | 80.8834 | 107.25 | 8.4583 | 25.1667 | 41.875 | 55.5 | 9.4413 | 26.984 | 44.5267 | 59.0417 | 121.6245 | 243.249 | 364.8735 | 486.498
Actual PMs
Actual Cost (K€)
Forecasted Cost (K€)
| Target Travel (K€) | 6.4325 | 12.865 | 19.2975 | 25.73 | 0.7975 | 1.595 | 2.3925 | 3.19 | 0.7975 | 1.595 | 2.3925 | 3.19 | 0.7975 | 1.595 | 2.3925 | 3.19 | 0.7975 | 1.595 | 2.3925 | 3.19 | 0.7975 | 1.595 | 2.3925 | 3.19 | 0.7975 | 1.595 | 2.3925 | 3.19 | 1.6475 | 3.295 | 4.9425 | 6.59
Actual Travel (K€)
| Target Purchases (K€) | 25 | 50 | 75 | 100 | 25 | 50 | 75 | 100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Actual Purchases (K€) |  |  |  |  | 0
| Total Target (K€) | 275.4105 | 668.2613 | 1064.9263 | 1362.2697 | 50.1272 | 121.1444 | 195.9757 | 251.94 | 47.1407 | 145.4938 | 243.8469 | 278.69 | 17.4281 | 49.1265 | 80.8249 | 107.19 | 17.9478 | 50.6119 | 83.2759 | 110.44 | 9.2558 | 26.7617 | 44.2675 | 58.69 | 10.2388 | 28.579 | 46.9192 | 62.2317 | 123.272 | 246.544 | 369.816 | 493.088
Total Actual (K€)
Difference (K€)
WP7 SUSTAINABILITY | Target PMs | 3.4643 | 21.1571 | 42.85 | 56 | 0.14286 | 1.1714 | 2.4 | 3 | 0.39286 | 1.2714 | 2.35 | 3 | 0.39286 | 1.2714 | 2.35 | 3 | 0.39286 | 1.2714 | 2.35 | 3 | 0.78571 | 4.5429 | 9.1 | 12 | 1.3571 | 11.6286 | 24.3 | 32 | 0 | 0 | 0 | 0
| Target Cost (K€) | 20.0417 | 112 | 224.675 | 292.5833 | 1.0119 | 8.2976 | 17 | 21.25 | 2.8482 | 9.2179 | 17.0375 | 21.75 | 3.1429 | 10.1714 | 18.8 | 24 | 3.2411 | 10.4893 | 19.3875 | 24.75 | 3.6339 | 21.0107 | 42.0875 | 55.5 | 6.1637 | 52.8131 | 110.3625 | 145.3333 | 0 | 0 | 0 | 0
Actual PMs
Actual Cost (K€)
Forecasted Cost (K€)
| Target Travel (K€) | 4.785 | 9.57 | 14.355 | 19.14 | 0.7975 | 1.595 | 2.3925 | 3.19 | 0.7975 | 1.595 | 2.3925 | 3.19 | 0.7975 | 1.595 | 2.3925 | 3.19 | 0.7975 | 1.595 | 2.3925 | 3.19 | 0.7975 | 1.595 | 2.3925 | 3.19 | 0.7975 | 1.595 | 2.3925 | 3.19 | 0 | 0 | 0 | 0
Actual Travel (K€)
| Target Purchases (K€) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Actual Purchases (K€) |  |  |  |  | 0
| Total Target (K€) | 24.8267 | 121.57 | 239.03 | 311.7233 | 1.8094 | 9.8926 | 19.3925 | 24.44 | 3.6457 | 10.8129 | 19.43 | 24.94 | 3.9404 | 11.7664 | 21.1925 | 27.19 | 4.0386 | 12.0843 | 21.78 | 27.94 | 4.4314 | 22.6057 | 44.48 | 58.69 | 6.9612 | 54.4081 | 112.755 | 148.5233 | 0 | 0 | 0 | 0
Total Actual (K€)
Difference (K€)
WP8 TRAINING | Target PMs | 13.5 | 32.8 | 91.6 | 108 | 0 | 1.4 | 4.8 | 6 | 0 | 1.9 | 7.3 | 9 | 0 | 0.9 | 3.3 | 4 | 9 | 16.6 | 29.2 | 35 | 4.5 | 10.6 | 42.2 | 48 | 0 | 1.4 | 4.8 | 6 | 0 | 0 | 0 | 0
| Target Cost (K€) | 95.0625 | 223.225 | 571.2 | 677.75 | 0 | 9.9167 | 34 | 42.5 | 0 | 13.775 | 52.925 | 65.25 | 0 | 7.2 | 26.4 | 32 | 74.25 | 136.95 | 240.9 | 288.75 | 20.8125 | 49.025 | 195.175 | 222 | 0 | 6.3583 | 21.8 | 27.25 | 0 | 0 | 0 | 0
Actual PMs
Actual Cost (K€)
Forecasted Cost (K€)
| Target Travel (K€) | 4.785 | 9.57 | 14.355 | 19.14 | 0.7975 | 1.595 | 2.3925 | 3.19 | 0.7975 | 1.595 | 2.3925 | 3.19 | 0.7975 | 1.595 | 2.3925 | 3.19 | 0.7975 | 1.595 | 2.3925 | 3.19 | 0.7975 | 1.595 | 2.3925 | 3.19 | 0.7975 | 1.595 | 2.3925 | 3.19 | 0 | 0 | 0 | 0
Actual Travel (K€)
| Target Purchases (K€) | 12.5 | 25 | 37.5 | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12.5 | 25 | 37.5 | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Actual Purchases (K€) |  |  |  |  | 0
| Total Target (K€) | 112.3475 | 257.795 | 623.055 | 746.89 | 0.7975 | 11.5117 | 36.3925 | 45.69 | 0.7975 | 15.37 | 55.3175 | 68.44 | 0.7975 | 8.795 | 28.7925 | 35.19 | 75.0475 | 138.545 | 243.2925 | 291.94 | 34.11 | 75.62 | 235.0675 | 275.19 | 0.7975 | 7.9533 | 24.1925 | 30.44 | 0 | 0 | 0 | 0
Total Actual (K€)
Difference (K€)
WP9 COMMUNICATION | Target PMs | 13 | 32 | 51 | 70 | 1 | 2.6667 | 4.3333 | 6 | 1 | 2.6667 | 4.3333 | 6 | 1 | 2.6667 | 4.3333 | 6 | 1 | 2.6667 | 4.3333 | 6 | 1 | 2.6667 | 4.3333 | 6 | 8 | 18.6667 | 29.3333 | 40 | 0 | 0 | 0 | 0
| Target Cost (K€) | 71.5417 | 178.6667 | 285.7917 | 392.9167 | 7.0833 | 18.8889 | 30.6944 | 42.5 | 7.25 | 19.3333 | 31.4167 | 43.5 | 8 | 21.3333 | 34.6667 | 48 | 8.25 | 22 | 35.75 | 49.5 | 4.625 | 12.3333 | 20.0417 | 27.75 | 36.3333 | 84.7778 | 133.2222 | 181.6667 | 0 | 0 | 0 | 0
Actual PMs
Actual Cost (K€)
Forecasted Cost (K€)
| Target Travel (K€) | 25.96 | 51.92 | 77.88 | 103.84 | 3.74 | 7.48 | 11.22 | 14.96 | 3.74 | 7.48 | 11.22 | 14.96 | 3.74 | 7.48 | 11.22 | 14.96 | 3.74 | 7.48 | 11.22 | 14.96 | 3.74 | 7.48 | 11.22 | 14.96 | 7.26 | 14.52 | 21.78 | 29.04 | 0 | 0 | 0 | 0
Actual Travel (K€)
| Target Purchases (K€) | 27.75 | 55.5 | 83.25 | 111 | 2.375 | 4.75 | 7.125 | 9.5 | 2.375 | 4.75 | 7.125 | 9.5 | 2.375 | 4.75 | 7.125 | 9.5 | 2.375 | 4.75 | 7.125 | 9.5 | 2.375 | 4.75 | 7.125 | 9.5 | 15.875 | 31.75 | 47.625 | 63.5 | 0 | 0 | 0 | 0
| Actual Purchases (K€) |  |  |  |  | 0
| Total Target (K€) | 125.2517 | 286.0867 | 446.9217 | 607.7567 | 13.1983 | 31.1189 | 49.0394 | 66.96 | 13.365 | 31.5633 | 49.7617 | 67.96 | 14.115 | 33.5633 | 53.0117 | 72.46 | 14.365 | 34.23 | 54.095 | 73.96 | 10.74 | 24.5633 | 38.3867 | 52.21 | 59.4683 | 131.0478 | 202.6272 | 274.2067 | 0 | 0 | 0 | 0
Total Actual (K€)
Difference (K€)
TOTAL | Target PMs | 262.4569 | 668.4658 | 1080.5438 | 1385 | 45.1746 | 105.9102 | 155.3555 | 203 | 34.8245 | 92.5062 | 156.1888 | 197 | 32.7795 | 79.2543 | 129.4333 | 176 | 38.8848 | 92.5853 | 146.3031 | 180 | 45.4959 | 119.3723 | 205.9595 | 253 | 44.7978 | 137.8376 | 225.8036 | 294 | 20.5 | 41 | 61.5 | 82
| Target Cost (K€) | 1690.9983 | 4240.0881 | 6818.2313 | 8751.0397 | 319.9867 | 750.1972 | 1100.4345 | 1437.9167 | 252.4774 | 670.67 | 1132.3689 | 1428.25 | 262.2356 | 634.0345 | 1035.4668 | 1408 | 320.7993 | 763.8283 | 1207.0006 | 1485 | 210.4183 | 552.0968 | 952.5626 | 1170.125 | 203.4565 | 626.0123 | 1025.5245 | 1335.25 | 121.6245 | 243.249 | 364.8735 | 486.498
| Actual PMs |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Actual Cost (K€) |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Forecasted Cost (K€) |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Target Travel (K€) | 121.2312 | 242.4625 | 363.6937 | 484.925 | 14.7262 | 29.4525 | 44.1787 | 58.905 | 14.7262 | 29.4525 | 44.1787 | 58.905 | 20.2262 | 40.4525 | 60.6788 | 80.905 | 14.7262 | 29.4525 | 44.1787 | 58.905 | 23.5262 | 47.0525 | 70.5787 | 94.105 | 27.0462 | 54.0925 | 81.1387 | 108.185 | 6.2538 | 12.5075 | 18.7613 | 25.015
| Actual Travel (K€) |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Target Purchases (K€) | 82.45 | 164.9 | 247.35 | 329.8 | 31.2 | 62.4 | 93.6 | 124.8 | 3.75 | 7.5 | 11.25 | 15 | 5.625 | 11.25 | 16.875 | 22.5 | 5.875 | 11.75 | 17.625 | 23.5 | 17.125 | 34.25 | 51.375 | 68.5 | 18.125 | 36.25 | 54.375 | 72.5 | 0.75 | 1.5 | 2.25 | 3
| Total Target (K€) | 1894.6796 | 4647.4506 | 7429.2751 | 9565.7647 | 365.913 | 842.0497 | 1238.2133 | 1621.6217 | 270.9537 | 707.6225 | 1187.7977 | 1502.155 | 288.0869 | 685.737 | 1113.0205 | 1511.405 | 341.4005 | 805.0308 | 1268.8043 | 1567.405 | 251.0696 | 633.3993 | 1074.5163 | 1332.73 | 248.6278 | 716.3548 | 1161.0382 | 1515.935 | 128.6282 | 257.2565 | 385.8847 | 514.513
| Total Actual (K€) |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Difference (K€) |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Note on B8: BODERA SEMPERE Jordi: This is the Actual PMs * average expected cost of a PM
Note on B121: BODERA SEMPERE Jordi: Please note this is without Overheads

## PaNOSC budget
|  |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7
|  |  | Total | ESRF | ILL | XFEL.EU | ESS | ELI | CERIC | EGI |  | Start month | End month | Length in months | start -1 | ESRF |  |  |  |  | ILL |  |  |  |  | XFEL.EU |  |  |  |  | ESS |  |  |  |  | ELI |  |  |  |  | CERIC |  |  |  |  | EGI
[16 empty] | 0 | 12 | 24 | 36 | 48 | 0 | 12 | 24 | 36 | 48 | 0 | 12 | 24 | 36 | 48 | 0 | 12 | 24 | 36 | 48 | 0 | 12 | 24 | 36 | 48 | 0 | 12 | 24 | 36 | 48 | 0 | 12 | 24 | 36 | 48
WP1 Management | T1.1 | Creation of PID and Executive Committee | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 2 | 2 | 0 |  | 2 | 2 | 2 | 2 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
| T1.2 | Project Management and coordination | 28 | 28 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 48 | 48 | 0 |  | 7 | 14 | 21 | 28 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
| T1.3 | Administration and local coordination | 34 | 19 | 3 | 3 | 3 | 3 | 3 | 0 |  | 1 | 48 | 48 | 0 |  | 4.75 | 9.5 | 14.25 | 19 |  | 0.75 | 1.5 | 2.25 | 3 |  | 0.75 | 1.5 | 2.25 | 3 |  | 0.75 | 1.5 | 2.25 | 3 |  | 0.75 | 1.5 | 2.25 | 3 |  | 0.75 | 1.5 | 2.25 | 3 |  | 0 | 0 | 0 | 0
|  | Sub-total | 64 | 49 | 3 | 3 | 3 | 3 | 3 | 0 | 4.621% | [5 empty] | 13.75 | 25.5 | 37.25 | 49 |  | 0.75 | 1.5 | 2.25 | 3 |  | 0.75 | 1.5 | 2.25 | 3 |  | 0.75 | 1.5 | 2.25 | 3 |  | 0.75 | 1.5 | 2.25 | 3 |  | 0.75 | 1.5 | 2.25 | 3 |  | 0 | 0 | 0 | 0
WP2 Data Policy and Stewardship
| T2.1 | Lesson learned and FAI Definitions | 6 | 1 | 1 | 0 | 1 | 1 | 2 | 0 |  | 1 | 6 | 6 | 0 |  | 1 | 1 | 1 | 1 |  | 1 | 1 | 1 | 1 |  | 0 | 0 | 0 | 0 |  | 1 | 1 | 1 | 1 |  | 1 | 1 | 1 | 1 |  | 2 | 2 | 2 | 2 |  | 0 | 0 | 0 | 0
| T2.2 | Update PaNOSC data policy framework | 8 | 2 | 1 | 1 | 2 | 1 | 1 | 0 |  | 6 | 18 | 13 | 5 |  | 1.0769 | 2 | 2 | 2 |  | 0.53846 | 1 | 1 | 1 |  | 0.53846 | 1 | 1 | 1 |  | 1.0769 | 2 | 2 | 2 |  | 0.53846 | 1 | 1 | 1 |  | 0.53846 | 1 | 1 | 1 |  | 0 | 0 | 0 | 0
| T2.3 | Aprove Data Policy framework | 12 | 1 | 1 | 1 | 1 | 6 | 2 | 0 |  | 9 | 36 | 28 | 8 |  | 0.14286 | 0.57143 | 1 | 1 |  | 0.14286 | 0.57143 | 1 | 1 |  | 0.14286 | 0.57143 | 1 | 1 |  | 0.14286 | 0.57143 | 1 | 1 |  | 0.85714 | 3.4286 | 6 | 6 |  | 0.28571 | 1.1429 | 2 | 2 |  | 0 | 0 | 0 | 0
| T2.4 | Create Guidelines | 20 | 9 | 1 | 1 | 4 | 3 | 2 | 0 |  | 1 | 24 | 24 | 0 |  | 4.5 | 9 | 9 | 9 |  | 0.5 | 1 | 1 | 1 |  | 0.5 | 1 | 1 | 1 |  | 2 | 4 | 4 | 4 |  | 1.5 | 3 | 3 | 3 |  | 1 | 2 | 2 | 2 |  | 0 | 0 | 0 | 0
| T2.5 | Implement DMP template | 22 | 2 | 6 | 0 | 6 | 6 | 2 | 0 |  | 12 | 36 | 25 | 11 |  | 0.08 | 1.04 | 2 | 2 |  | 0.24 | 3.12 | 6 | 6 |  | 0 | 0 | 0 | 0 |  | 0.24 | 3.12 | 6 | 6 |  | 0.24 | 3.12 | 6 | 6 |  | 0.08 | 1.04 | 2 | 2 |  | 0 | 0 | 0 | 0
| T2.6 | Validation of Data Policy implementation | 8 | 2 | 0 | 0 | 0 | 3 | 3 | 0 |  | 12 | 36 | 25 | 11 |  | 0.08 | 1.04 | 2 | 2 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0.12 | 1.56 | 3 | 3 |  | 0.12 | 1.56 | 3 | 3 |  | 0 | 0 | 0 | 0
|  | Sub-total | 76 | 17 | 10 | 3 | 14 | 20 | 12 | 0 | 5.487% | [5 empty] | 6.8798 | 14.6514 | 17 | 17 |  | 2.4213 | 6.6914 | 10 | 10 |  | 1.1813 | 2.5714 | 3 | 3 |  | 4.4598 | 10.6914 | 14 | 14 |  | 4.2556 | 13.1086 | 20 | 20 |  | 4.0242 | 8.7429 | 12 | 12 |  | 0 | 0 | 0 | 0
WP3 Data Catalog Services | T3.1 | Develop API | 59 | 1 | 9 | 6 | 15 | 14 | 14 | 0 |  | 1 | 28 | 28 | 0 |  | 0.42857 | 0.85714 | 1 | 1 |  | 3.8571 | 7.7143 | 9 | 9 |  | 2.5714 | 5.1429 | 6 | 6 |  | 6.4286 | 12.8571 | 15 | 15 |  | 6 | 12 | 14 | 14 |  | 6 | 12 | 14 | 14 |  | 0 | 0 | 0 | 0
|  | merged with T3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 1 | -1
|  | merged with T3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 1 | -1
| T3.2 | Provisioning Federated search | 39 | 0 | 3 | 0 | 10 | 20 | 6 | 0 |  | 8 | 20 | 13 | 7 |  | 0 | 0 | 0 | 0 |  | 1.1538 | 3 | 3 | 3 |  | 0 | 0 | 0 | 0 |  | 3.8462 | 10 | 10 | 10 |  | 7.6923 | 20 | 20 | 20 |  | 2.3077 | 6 | 6 | 6 |  | 0 | 0 | 0 | 0
| T3.3 | Local Deployment | 36 | 6 | 6 | 6 | 6 | 6 | 6 | 0 |  | 20 | 44 | 25 | 19 |  | 0 | 1.2 | 4.08 | 6 |  | 0 | 1.2 | 4.08 | 6 |  | 0 | 1.2 | 4.08 | 6 |  | 0 | 1.2 | 4.08 | 6 |  | 0 | 1.2 | 4.08 | 6 |  | 0 | 1.2 | 4.08 | 6 |  | 0 | 0 | 0 | 0
| T3.4 | Catalog integration | 88 | 12 | 0 | 6 | 0 | 20 | 50 | 0 |  | 12 | 48 | 37 | 11 |  | 0.32432 | 4.2162 | 8.1081 | 12 |  | 0 | 0 | 0 | 0 |  | 0.16216 | 2.1081 | 4.0541 | 6 |  | 0 | 0 | 0 | 0 |  | 0.54054 | 7.027 | 13.5135 | 20 |  | 1.3514 | 17.5676 | 33.7838 | 50 |  | 0 | 0 | 0 | 0
| T3.5 | Meta Anthology for Catalogues | 69 | 6 | 3 | 18 | 12 | 18 | 12 | 0 |  | 1 | 42 | 42 | 0 |  | 1.7143 | 3.4286 | 5.1429 | 6 |  | 0.85714 | 1.7143 | 2.5714 | 3 |  | 5.1429 | 10.2857 | 15.4286 | 18 |  | 3.4286 | 6.8571 | 10.2857 | 12 |  | 5.1429 | 10.2857 | 15.4286 | 18 |  | 3.4286 | 6.8571 | 10.2857 | 12 |  | 0 | 0 | 0 | 0
|  | Sub-total | 291 | 25 | 21 | 36 | 43 | 78 | 88 | 0 | 21.01% | [5 empty] | 2.4672 | 9.7019 | 18.331 | 25 |  | 5.8681 | 13.6286 | 18.6514 | 21 |  | 7.8764 | 18.7367 | 29.5626 | 36 |  | 13.7033 | 30.9143 | 39.3657 | 43 |  | 19.3757 | 50.5127 | 67.0221 | 78 |  | 13.0876 | 43.6247 | 68.1495 | 88 |  | 0 | 0 | 0 | 0
WP4 Data Analysis Services | T4.1 | Survey | 9 | 1 | 3 | 2 | 1 | 1 | 1 | 0 |  | 1 | 12 | 12 | 0 |  | 1 | 1 | 1 | 1 |  | 3 | 3 | 3 | 3 |  | 2 | 2 | 2 | 2 |  | 1 | 1 | 1 | 1 |  | 1 | 1 | 1 | 1 |  | 1 | 1 | 1 | 1 |  | 0 | 0 | 0 | 0
| T4.2 | Remote Desktop based analysis services | 66 | 0 | 36 | 0 | 12 | 0 | 18 | 0 |  | 1 | 36 | 36 | 0 |  | 0 | 0 | 0 | 0 |  | 12 | 24 | 36 | 36 |  | 0 | 0 | 0 | 0 |  | 4 | 8 | 12 | 12 |  | 0 | 0 | 0 | 0 |  | 6 | 12 | 18 | 18 |  | 0 | 0 | 0 | 0
| T4.3 | EOSC integration and common portal | 39 | 6 | 6 | 2 | 6 | 6 | 13 | 0 |  | 13 | 48 | 36 | 12 |  | 0 | 2 | 4 | 6 |  | 0 | 2 | 4 | 6 |  | 0 | 0.66667 | 1.3333 | 2 |  | 0 | 2 | 4 | 6 |  | 0 | 2 | 4 | 6 |  | 0 | 4.3333 | 8.6667 | 13 |  | 0 | 0 | 0 | 0
| T4.4 | Jupyter based analysis services | 124 | 22 | 12 | 42 | 6 | 30 | 12 | 0 |  | 1 | 48 | 48 | 0 |  | 5.5 | 11 | 16.5 | 22 |  | 3 | 6 | 9 | 12 |  | 10.5 | 21 | 31.5 | 42 |  | 1.5 | 3 | 4.5 | 6 |  | 7.5 | 15 | 22.5 | 30 |  | 3 | 6 | 9 | 12 |  | 0 | 0 | 0 | 0
| T4.5 | Deployment | 60 | 6 | 12 | 12 | 6 | 12 | 12 | 0 |  | 13 | 48 | 36 | 12 |  | 0 | 2 | 4 | 6 |  | 0 | 4 | 8 | 12 |  | 0 | 4 | 8 | 12 |  | 0 | 2 | 4 | 6 |  | 0 | 4 | 8 | 12 |  | 0 | 4 | 8 | 12 |  | 0 | 0 | 0 | 0
| T4.6 | Demonstrator | 11 | 1 | 2 | 2 | 1 | 1 | 4 | 0 |  | 37 | 48 | 12 | 36 |  | 0 | 0 | 0 | 1 |  | 0 | 0 | 0 | 2 |  | 0 | 0 | 0 | 2 |  | 0 | 0 | 0 | 1 |  | 0 | 0 | 0 | 1 |  | 0 | 0 | 0 | 4 |  | 0 | 0 | 0 | 0
|  | Sub-total | 309 | 36 | 71 | 60 | 32 | 50 | 60 | 0 | 22.31% | [5 empty] | 6.5 | 16 | 25.5 | 36 |  | 18 | 39 | 60 | 71 |  | 12.5 | 27.6667 | 42.8333 | 60 |  | 6.5 | 16 | 25.5 | 32 |  | 8.5 | 22 | 35.5 | 50 |  | 10 | 27.3333 | 44.6667 | 60 |  | 0 | 0 | 0 | 0
WP5 Virtual Neutron and X-ray Laboratory | T5.1 | Simulation Infrastructure | 36 | 4 | 0 | 24 | 4 | 0 | 4 | 0 |  | 1 | 48 | 48 | 0 |  | 1 | 2 | 3 | 4 |  | 0 | 0 | 0 | 0 |  | 6 | 12 | 18 | 24 |  | 1 | 2 | 3 | 4 |  | 0 | 0 | 0 | 0 |  | 1 | 2 | 3 | 4 |  | 0 | 0 | 0 | 0
| T5.2 | Source simulation services | 40 | 20 | 0 | 2 | 0 | 9 | 9 | 0 |  | 1 | 24 | 24 | 0 |  | 10 | 20 | 20 | 20 |  | 0 | 0 | 0 | 0 |  | 1 | 2 | 2 | 2 |  | 0 | 0 | 0 | 0 |  | 4.5 | 9 | 9 | 9 |  | 4.5 | 9 | 9 | 9 |  | 0 | 0 | 0 | 0
| T5.3 | Beamline simulation services | 52 | 6 | 12 | 8 | 10 | 0 | 16 | 0 |  | 13 | 36 | 24 | 12 |  | 0 | 3 | 6 | 6 |  | 0 | 6 | 12 | 12 |  | 0 | 4 | 8 | 8 |  | 0 | 5 | 10 | 10 |  | 0 | 0 | 0 | 0 |  | 0 | 8 | 16 | 16 |  | 0 | 0 | 0 | 0
| T5.4 | Signal generation simulation | 53 | 0 | 12 | 8 | 13 | 15 | 5 | 0 |  | 25 | 48 | 24 | 24 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 6 | 12 |  | 0 | 0 | 4 | 8 |  | 0 | 0 | 6.5 | 13 |  | 0 | 0 | 7.5 | 15 |  | 0 | 0 | 2.5 | 5 |  | 0 | 0 | 0 | 0
| T5.5 | Simulation data workflows | 38 | 10 | 12 | 6 | 4 | 0 | 6 | 0 |  | 37 | 48 | 12 | 36 |  | 0 | 0 | 0 | 10 |  | 0 | 0 | 0 | 12 |  | 0 | 0 | 0 | 6 |  | 0 | 0 | 0 | 4 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 6 |  | 0 | 0 | 0 | 0
|  | Sub-total | 219 | 40 | 36 | 48 | 31 | 24 | 40 | 0 | 15.81% | [5 empty] | 11 | 25 | 29 | 40 |  | 0 | 6 | 18 | 36 |  | 7 | 18 | 32 | 48 |  | 1 | 7 | 19.5 | 31 |  | 4.5 | 9 | 16.5 | 24 |  | 5.5 | 19 | 30.5 | 40 |  | 0 | 0 | 0 | 0
WP6 EOSC Integration | T6.1 | Management of the integration with e-Infrastructures | 7 | 1 | 6 | 0 | 0 | 0 | 0 | 0 |  | 1 | 48 | 48 | 0 |  | 0.25 | 0.5 | 0.75 | 1 |  | 1.5 | 3 | 4.5 | 6 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
| T6.2 | EOSC Hub Service Catalogue | 16 | 6 | 2 | 2 | 2 | 2 | 2 | 0 |  | 1 | 48 | 48 | 0 |  | 1.5 | 3 | 4.5 | 6 |  | 0.5 | 1 | 1.5 | 2 |  | 0.5 | 1 | 1.5 | 2 |  | 0.5 | 1 | 1.5 | 2 |  | 0.5 | 1 | 1.5 | 2 |  | 0.5 | 1 | 1.5 | 2 |  | 0 | 0 | 0 | 0
| T6.3 | Data availability for services | 17 | 3 | 3 | 3 | 3 | 2 | 3 | 0 |  | 1 | 48 | 48 | 0 |  | 0.75 | 1.5 | 2.25 | 3 |  | 0.75 | 1.5 | 2.25 | 3 |  | 0.75 | 1.5 | 2.25 | 3 |  | 0.75 | 1.5 | 2.25 | 3 |  | 0.5 | 1 | 1.5 | 2 |  | 0.75 | 1.5 | 2.25 | 3 |  | 0 | 0 | 0 | 0
| T6.4 | AAI Integration | 19 | 2 | 9 | 2 | 2 | 2 | 2 | 0 |  | 1 | 36 | 36 | 0 |  | 0.66667 | 1.3333 | 2 | 2 |  | 3 | 6 | 9 | 9 |  | 0.66667 | 1.3333 | 2 | 2 |  | 0.66667 | 1.3333 | 2 | 2 |  | 0.66667 | 1.3333 | 2 | 2 |  | 0.66667 | 1.3333 | 2 | 2 |  | 0 | 0 | 0 | 0
| T6.5 | Services Support | 34 | 4 | 6 | 6 | 6 | 6 | 6 | 0 |  | 12 | 48 | 37 | 11 |  | 0.10811 | 1.4054 | 2.7027 | 4 |  | 0.16216 | 2.1081 | 4.0541 | 6 |  | 0.16216 | 2.1081 | 4.0541 | 6 |  | 0.16216 | 2.1081 | 4.0541 | 6 |  | 0.16216 | 2.1081 | 4.0541 | 6 |  | 0.16216 | 2.1081 | 4.0541 | 6 |  | 0 | 0 | 0 | 0
| T6.6 | PaN Software Catalogue | 16 | 4 | 12 | 0 | 0 | 0 | 0 | 0 |  | 12 | 36 | 25 | 11 |  | 0.16 | 2.08 | 4 | 4 |  | 0.48 | 6.24 | 12 | 12 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
| T6.7 | Data archiving pilot | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 12 | 48 | 37 | 11 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
| T6.8 | Procure commercial cloud | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 |  | 30 | 42 | 13 | 29 |  | 0 | 0 | 0.53846 | 1 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
|  | Sub-total | 192 | 21 | 38 | 13 | 13 | 12 | 13 | 82 | 13.86% | [5 empty] | 3.4348 | 9.8187 | 16.7412 | 21 |  | 6.3922 | 19.8481 | 33.3041 | 38 |  | 2.0788 | 5.9414 | 9.8041 | 13 |  | 2.0788 | 5.9414 | 9.8041 | 13 |  | 1.8288 | 5.4414 | 9.0541 | 12 |  | 2.0788 | 5.9414 | 9.8041 | 13 |  | 20.5 | 41 | 61.5 | 82
WP7 Sustainibility | T7.1 | Stakeholder definition | 7 | 0 | 1 | 1 | 1 | 2 | 2 | 0 |  | 1 | 48 | 48 | 0 |  | 0 | 0 | 0 | 0 |  | 0.25 | 0.5 | 0.75 | 1 |  | 0.25 | 0.5 | 0.75 | 1 |  | 0.25 | 0.5 | 0.75 | 1 |  | 0.5 | 1 | 1.5 | 2 |  | 0.5 | 1 | 1.5 | 2 |  | 0 | 0 | 0 | 0
| T7.2 | Metrics and costs | 12 | 1 | 1 | 1 | 1 | 2 | 6 | 0 |  | 9 | 36 | 28 | 8 |  | 0.14286 | 0.57143 | 1 | 1 |  | 0.14286 | 0.57143 | 1 | 1 |  | 0.14286 | 0.57143 | 1 | 1 |  | 0.14286 | 0.57143 | 1 | 1 |  | 0.28571 | 1.1429 | 2 | 2 |  | 0.85714 | 3.4286 | 6 | 6 |  | 0 | 0 | 0 | 0
| T7.3 | Business models | 17 | 1 | 0 | 0 | 0 | 4 | 12 | 0 |  | 13 | 42 | 30 | 12 |  | 0 | 0.4 | 0.8 | 1 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 | 1.6 | 3.2 | 4 |  | 0 | 4.8 | 9.6 | 12 |  | 0 | 0 | 0 | 0
| T7.4 | Sustainability plan | 20 | 1 | 1 | 1 | 1 | 4 | 12 | 0 |  | 19 | 48 | 30 | 18 |  | 0 | 0.2 | 0.6 | 1 |  | 0 | 0.2 | 0.6 | 1 |  | 0 | 0.2 | 0.6 | 1 |  | 0 | 0.2 | 0.6 | 1 |  | 0 | 0.8 | 2.4 | 4 |  | 0 | 2.4 | 7.2 | 12 |  | 0 | 0 | 0 | 0
|  | Sub-total | 56 | 3 | 3 | 3 | 3 | 12 | 32 | 0 | 4.043% | [5 empty] | 0.14286 | 1.1714 | 2.4 | 3 |  | 0.39286 | 1.2714 | 2.35 | 3 |  | 0.39286 | 1.2714 | 2.35 | 3 |  | 0.39286 | 1.2714 | 2.35 | 3 |  | 0.78571 | 4.5429 | 9.1 | 12 |  | 1.3571 | 11.6286 | 24.3 | 32 |  | 0 | 0 | 0 | 0
Staff training in data stewardship | T8.1 | Sustainability and maintainability | 18 | 0 | 0 | 0 | 12 | 6 | 0 | 0 |  | 4 | 15 | 12 | 3 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 9 | 12 | 12 | 12 |  | 4.5 | 6 | 6 | 6 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
| T8.2 | Integrate Jupyter technology | 20 | 2 | 3 | 1 | 6 | 6 | 2 | 0 |  | 19 | 30 | 12 | 18 |  | 0 | 1 | 2 | 2 |  | 0 | 1.5 | 3 | 3 |  | 0 | 0.5 | 1 | 1 |  | 0 | 3 | 6 | 6 |  | 0 | 3 | 6 | 6 |  | 0 | 1 | 2 | 2 |  | 0 | 0 | 0 | 0
| T8.3 | Integrate ESFRIs | 15 |  |  |  | 3 | 12 | 0 | 0 |  | 25 | 36 | 12 | 24 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 3 | 3 |  | 0 | 0 | 12 | 12 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
| T8.4 | Staff training in e-learning platform | 12 | 1 | 1 | 1 | 4 | 4 | 1 | 0 |  | 13 | 42 | 30 | 12 |  | 0 | 0.4 | 0.8 | 1 |  | 0 | 0.4 | 0.8 | 1 |  | 0 | 0.4 | 0.8 | 1 |  | 0 | 1.6 | 3.2 | 4 |  | 0 | 1.6 | 3.2 | 4 |  | 0 | 0.4 | 0.8 | 1 |  | 0 | 0 | 0 | 0
| T8.5 | Staff training in data stewardship | 17 | 1 | 2 | 1 | 2 | 10 | 1 | 0 |  | 25 | 32 | 8 | 24 |  | 0 | 0 | 1 | 1 |  | 0 | 0 | 2 | 2 |  | 0 | 0 | 1 | 1 |  | 0 | 0 | 2 | 2 |  | 0 | 0 | 10 | 10 |  | 0 | 0 | 1 | 1 |  | 0 | 0 | 0 | 0
| T8.6 | Training materials to foster the uptake of PaNOSC services | 21 | 2 | 3 | 1 | 3 | 10 | 2 | 0 |  | 31 | 42 | 12 | 30 |  | 0 | 0 | 1 | 2 |  | 0 | 0 | 1.5 | 3 |  | 0 | 0 | 0.5 | 1 |  | 0 | 0 | 1.5 | 3 |  | 0 | 0 | 5 | 10 |  | 0 | 0 | 1 | 2 |  | 0 | 0 | 0 | 0
| T8.7 | Introductory course to materials science | 3 |  |  |  | 3 |  |  |  |  | 31 | 42 | 12 | 30 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 1.5 | 3 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
| T8.8 | PaNOSC schools for students | 2 |  |  |  | 2 |  |  |  |  | 42 | 48 | 7 | 41 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 2 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
|  | Sub-total | 108 | 6 | 9 | 4 | 35 | 48 | 6 | 0 | 7.798% | [5 empty] | 0 | 1.4 | 4.8 | 6 |  | 0 | 1.9 | 7.3 | 9 |  | 0 | 0.9 | 3.3 | 4 |  | 9 | 16.6 | 29.2 | 35 |  | 4.5 | 10.6 | 42.2 | 48 |  | 0 | 1.4 | 4.8 | 6 |  | 0 | 0 | 0 | 0
WP9 Outreach &Communication | T9.1 | Internal and external communication | 34 | 2 | 2 | 2 | 2 | 2 | 24 | 0 |  | 1 | 48 | 48 | 0 |  | 0.5 | 1 | 1.5 | 2 |  | 0.5 | 1 | 1.5 | 2 |  | 0.5 | 1 | 1.5 | 2 |  | 0.5 | 1 | 1.5 | 2 |  | 0.5 | 1 | 1.5 | 2 |  | 6 | 12 | 18 | 24 |  | 0 | 0 | 0 | 0
| T9.2 | Dissemination of results | 18 | 2 | 2 | 2 | 2 | 2 | 8 | 0 |  | 13 | 48 | 36 | 12 |  | 0 | 0.66667 | 1.3333 | 2 |  | 0 | 0.66667 | 1.3333 | 2 |  | 0 | 0.66667 | 1.3333 | 2 |  | 0 | 0.66667 | 1.3333 | 2 |  | 0 | 0.66667 | 1.3333 | 2 |  | 0 | 2.6667 | 5.3333 | 8 |  | 0 | 0 | 0 | 0
| T9.3 | Collaboration actions with other clusters | 18 | 2 | 2 | 2 | 2 | 2 | 8 | 0 |  | 1 | 48 | 48 | 0 |  | 0.5 | 1 | 1.5 | 2 |  | 0.5 | 1 | 1.5 | 2 |  | 0.5 | 1 | 1.5 | 2 |  | 0.5 | 1 | 1.5 | 2 |  | 0.5 | 1 | 1.5 | 2 |  | 2 | 4 | 6 | 8 |  | 0 | 0 | 0 | 0
|  | Sub-total | 70 | 6 | 6 | 6 | 6 | 6 | 40 | 0 | 5.054% | [5 empty] | 1 | 2.6667 | 4.3333 | 6 |  | 1 | 2.6667 | 4.3333 | 6 |  | 1 | 2.6667 | 4.3333 | 6 |  | 1 | 2.6667 | 4.3333 | 6 |  | 1 | 2.6667 | 4.3333 | 6 |  | 8 | 18.6667 | 29.3333 | 40 |  | 0 | 0 | 0 | 0
|  | Remaining Person Months |  | -15.1583 | 1.6665 | 0.354 | -6.4446 | 39.2448 | -0.37387 |  | Red if too high, Green otherwise |  |  |  |  | TOTAL PM | 45.1746 | 105.9102 | 155.3555 | 203 |  | 34.8245 | 92.5062 | 156.1888 | 197 |  | 32.7795 | 79.2543 | 129.4333 | 176 |  | 38.8848 | 92.5853 | 146.3031 | 180 |  | 45.4959 | 119.3723 | 205.9595 | 253 |  | 44.7978 | 137.8376 | 225.8036 | 294 |  | 20.5 | 41 | 61.5 | 82
|  | PM Total WPs | 1385 | 203 | 197 | 176 | 180 | 253 | 294 | 82 | [5 empty] | Total PM Cost | 319.9867 | 750.1972 | 1100.4345 | 1437.9167 |  | 252.4774 | 670.67 | 1132.3689 | 1428.25 |  | 262.2356 | 634.0345 | 1035.4668 | 1408 |  | 320.7993 | 763.8283 | 1207.0006 | 1485 |  | 210.4183 | 552.0968 | 952.5626 | 1170.125 |  | 203.4565 | 626.0123 | 1025.5245 | 1335.25 |  | 152.0306 | 304.0612 | 456.0919 | 608.1225
|  | PY Total WPs | 115.4167 | 16.9167 | 16.4167 | 14.6667 | 15 | 21.0833 | 24.5 | 6.8333
|  | Average yearly staff cost (kEUR) |  | 85000 | 87000 | 96000 | 99000 | 55500 | 54500 | varied | Green means validated
|  | Total in k€ for personnel (without overhead) | 8751039.6667 | 1437916.6667 | 1428250 | 1408000 | 1485000 | 1170125 | 1335250 | 486498
|  | Total in K€ for personal (with +25% overheads) | 10938799.5833 | 1797395.8333 | 1785312.5 | 1760000 | 1856250 | 1462656.25 | 1669062.5 | 608122.5
|  | Travel cost | 484910 | 58905 | 58905 | 80905 | 58905 | 94105 | 108185 | 25000
|  | Purchases (allowing overheads) | 329800 | 124800 | 15000 | 22500 | 23500 | 68500 | 72500 | 3000
|  | Purchases NOT allowing overheads (subcontracting) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Total in k€ (+25% overhead, without non-funded partners) | 11957187.0833 | 2027027.0833 | 1877693.75 | 1889256.25 | 1959256.25 | 1665912.5 | 1894918.75 | 643122.5 | All partners expenditure up to (12M - EGI allowance)/6 = 1876k
|  | in % of total project | 100 | 16.9524 | 15.7035 | 15.8002 | 16.3856 | 13.9323 | 15.8475 | 5.3785
|  | Money left (up to 12m): (in kEUR) | 42812.9167
|  | Max number of Person Months per partner |  | 187.8417 | 198.6665 | 176.354 | 173.5554 | 292.2448 | 293.6261
Cost Breakdown
|  | Staff Costs | 10938799.5833
|  | Purchases | 412250
|  | Travel | 606137.5
Effort Breakdown
|  | WP1 Management | 4.621%
|  | WP2 Data Policy and Stewardship | 5.487%
|  | WP3 Data Catalog Services | 21.01%
|  | WP4 Data Analysis Services | 22.31%
|  | WP5 Virtual Neutron and X-ray Laboratory | 15.81%
|  | WP6 EOSC Integration | 13.86%
|  | WP7 Sustainibility | 4.043%
|  | Staff training in data stewardship | 7.798%
|  | WP9 Outreach &Communication | 5.054%

## EGI budget
85 | Duration [PY1-PY2] | Effort Distribution (PM) | TOT Effort (PMs) | Partner | PM Rate (euro) | (A) DIrect Personal Cost (Euro) | (B) Other direct cost (equipment, travel) | (C) Direct cost of subcontracting | (D) Indirect cost (=0.25* (A+B)) | Total estimated eligible costs (A+B+C+D) | Reimbursement rate
Cloud Compute | Special server (64 cores / 1 TB Ram) = 1000 Hours (for 1st Y) + 2000 H (2nd Y) + 4000 H (3rdY) + 10000 H (4th Y) ARCHIVING: 300 TB of tapes for open data backup | PY1-PY4 with capacity doubling every year | 24 | CESNET (Standard server only) | 4200 | 100800 | 0 | 0 | 25200 | 126000 |  | 378000
Cloud Compute | Standard server (16 cores/128 GB Ram) = 20000 Hours (for 1st Y) + 40000 H (2nd Y) + 100000 H (3rdY) + 200000 H (4th Y) ONLINE STORAGE: 50 TB ARCHIVING: 200 TB (can be increased, extra capacity needs to be invoiced) | PY1-PY4 with capacity doubling every year | 28 | DESY (special server only) | 7200 | 201600 | 0 | 0 | 50400 | 252000
Notebooks and Applications on Demand | Deployment and operation of Jupyter notebook service for PaNoSC community integrated with federated authentication, persistent storage for user notebooks, and access to PaNoSC datasets. | P1-P4 | 6 | EGI F | 7259 | 43554 | 0 | 0 | 10888.5 | 54442.5
Data transfer/FTS3 | . Alpha testing (YEAR 1): requirements analysis, piloting, porting of existing applications to FTS3, FTS3 operations: 4 PMs/YEAR 1. . Beta testing (YEAR 2,3,4): FTS3 operations in production, support to users and service providers: 1 PM from YEAR 2 till the end of the project | PY1: 4 PM PY2-3-4: 1 PM | 24 | STFC | 5856 | 140544 | 0 | 0 | 35136 | 175680
Archiving
TOTAL |  |  | 82 |  |  | 486498 | 25000 |  | 6250 | 639372.5
486498
71194.8293
|  |  |  | min | 50400
|  |  |  | max | 87108

## Budget Travel
Travel type | Travel cost | Daily Accommodation | Daily Subsistence | Avg. number of nights | Total pp | Persons per partner | Total per trip | Trips per year | Partner Annual Total | Partner total | Partner total | Notes
Between partners | 330 | 110 | 55 | 2 | 715 | 5 | 3575 | 1 | 3575 | 14300 | 14300 | all partners inc. EGI | WP1 | Calculation from OpenDreamKit for a site with 1 PI and 1 FTE
Within partner sites | 220 | 82.5 | 55 | 2 | 550 | 8 | 4400 | 2 | 8800 | 35200 | 35200 | Only for ELI and CERIC | WP1 | Calculation from OpenDreamKit
All partners to Brussels | 330 | 165 | 55 | 2 | 825 | 5 | 4125 | 0.25 | 1031.25 | 4125 | 4125 | all partners inc. EGI | WP1 |  |  | cost | FTE | PI | site | total per year
Annual conference Hosting | N/A | N/A | N/A | N/A | N/A | N/A | 0 | 1 | 0 | 0 | 0 | Moved to Purchases |  |  | Duration |  | per year | per year | per year
WP1 trips between partners | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | Only ESRF, not needed |  | Project meetings | 2 day | 400 | 2 | 2 |  | 1600
WP2 trips between partners | 330 | 82.5 | 55 | 3 | 797.5 | 2 | 1595 | 0.5 | 797.5 | 3190 | 3190 | all partners except EGI | WP2 | conference Europe | 5 day | 1200 | 2 | 1 |  | 3600
WP3 trips between partners | 330 | 82.5 | 55 | 3 | 797.5 | 2 | 1595 | 0.5 | 797.5 | 3190 | 3190 | all partners except EGI | WP3 | conference international | 5 day | 2250 | 1 | 1 |  | 4500
WP4 trips between partners | 330 | 82.5 | 55 | 3 | 797.5 | 2 | 1595 | 1 | 1595 | 6380 | 6380 | all partners except EGI | WP4 | project partner visit and coding sprints | 5 day | 750 | 4 | 4 |  | 6000
WP5 trips between partners | 330 | 82.5 | 55 | 3 | 797.5 | 2 | 1595 | 0.5 | 797.5 | 3190 | 3190 | all partners except EGI | WP5 | hosting international visitors |  | 2000 |  |  | 1 | 2000
WP6 trips between partners | 330 | 82.5 | 55 | 3 | 797.5 | 2 | 1595 | 0.5 | 797.5 | 3190 | 3190 | all partners inc. EGI | WP6
WP7 trips between partners | 330 | 82.5 | 55 | 3 | 797.5 | 2 | 1595 | 0.5 | 797.5 | 3190 | 3190 | all partners except EGI | WP7 | [5 empty] | total per year | 17700
WP8 trips between partners | 330 | 82.5 | 55 | 3 | 797.5 | 2 | 1595 | 0.5 | 797.5 | 3190 | 3190 | all partners except EGI | WP8 | [5 empty] | total over 4 years | 70800
WP9 travel for outreach | 330 | 110 | 55 | 3 | 880 | 2 | 1760 | 2 | 3520 | 14080 | 14080 | Only CERIC | WP9
European conference | 330 | 165 | 55 | 5 | 1485 | 2 | 2970 | 0.5 | 1485 | 5940 | 5940 | all partners except EGI | WP9
Overseas conference | 1100 | 165 | 55 | 5 | 2255 | 2 | 4510 | 0.5 | 2255 | 9020 | 9020 | all partners except EGI | WP9
Inviting/visiting Jupyter team (Oslo/Berkeley) | [8 empty] | 5500 | 22000 | 22000 | XFEL | WP4
- registration cost? (EOSCPilot meeting was only 100EUR, but it all accumulates)
- Registration cost for conferences considered in Purchases tab
Partners | Logic |  |  |  |  | Travel budget
ESRF | Travels between partners + WP trips |  |  |  |  | 58905 | 16.25 | Persons traveling per year
ILL | Travels between partners + WP trips |  |  |  |  | 58905 | 16.25 | Persons traveling per year
XFEL | Travels between partners + WP trips + inviting Jupyter team |  |  |  |  | 80905 | 16.25 | Persons traveling per year
ESS | Travels between partners + WP trips |  |  |  |  | 58905 | 16.25 | Persons traveling per year
ELI | Travels between partners + WP trips + within partner sites |  |  |  |  | 94105 | 32.25 | Persons traveling per year
CERIC | Travels between partners + WP trips + within partner sites + WP9 |  |  |  |  | 108185 | 36.25 | Persons traveling per year
EGI | Travel to participate in WP6 |  |  |  |  | 25000
TOTAL | [5 empty] | 484910 | 4.041% | of total budget
With overheads around 5%
for psicollogycal reasons lets try to be under half million

## Purchases
|  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7
Work Package | Purchase Name | Total | ESRF | ILL | XFEL | ESS | ELI | CERIC | EGI | Overheads possible?
1 | Project Management tool | Total: 0; ESRF: 0 | Y | ESRF will provide Jira to all partners for free
9 | Public site | Total: 30000; CERIC: 30000 | Y | Roberto broke down the figure as (Visual Identity 7k; Website 17k; Hosting and Support 6k)
6 | Cloud Tools & Services | Total: 100000; ESRF: 100000; EGI: 0 | Y
1 | CFS (Certificate Financial Statement) | 24800 | 1300 | 1500 | 4000 | 5000 | 5000 | 5000 | 3000 | Y | Green means validated
9 | Coms and promotional materials | Total: 24000; CERIC: 24000 | Y
8 | Training materials (e.g videos) | Total: 50000; ELI: 50000 | Y
1 | Annual conference not travel items | Total: 20000; ESRF: 10000; XFEL: 5000; ESS: 5000 | Y | Volunteers needed to take on 3k. For the time being assigned to XFEL and ESS and subject to approval
All (9) | Conference fees | 36000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 |  | Y
All (1) | Workshop organisation | 24000 | 4000 | 4000 | 4000 | 4000 | 4000 | 4000 |  | Y
9 | Open access publications | 21000 | 3500 | 3500 | 3500 | 3500 | 3500 | 3500 |  | Y
| Total (items allowing overheads) | 329800 | 124800 | 15000 | 22500 | 23500 | 68500 | 72500 | 3000
| Total (items NOT allowing overheads) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| TOTAL | 329800 | 124800 | 15000 | 22500 | 23500 | 68500 | 72500 | 3000
No overheads allowed for subcontracting
PLEASE NOTE: Column K explains for which items overheads (+25%) will be added in the main PaNOSC budget sheet

## Cloud services
Partner | Service | Machine Name | vCPUs | Memory (GBs) | Storage (GBs) | Simultaneous users | Price per hour | Hours per job | Cost per job | Price per day | Price per year | Price per 4 years | Reserved price | spot | total project
ESRF | Jupyter | r4.4xlarge | 16 | 122 |  | 20 | 1.0109 |  |  | 24.2611 | 8855.3088 | 35421.2352 |  |  | 0
ILL | Xrystal | r4.4xlarge | 2 | 128 |  | 1 | 1.0109 | 100 | 101.088 | 24.2611 | 8855.3088 | 35421.2352 |  |  | 93000.96
ESRF | Ptycho | x1.16xlarge | 64 | 976 |  | 1 | 5.6449 | 24 | 135.4774 | 135.4774 | 49449.2364 | 197796.9456 |  |  | 124639.1712
XFEL.EU | Ptycho (as ESRF) | x1.16xlarge | 64 | 976 | 0 | 1 | 5.6449 | 24 | 135.4774 | 135.4774 | 49449.2364 | 197796.9456 |  |  | 124639.1712
XFEL.EU | Jupyter (as ESRF) | r4.4xlarge | 16 | 122 | 0 | 20 | 1.0109 | 0 | 0 | 24.2611 | 8855.3088 | 35421.2352 |  |  | 0
XFEL.EU | SIMEX/WPG | x1.16xlarge | 64 | 976 |  | 0.125 | 5.6449 | 3 | 16.9347 | 16.9347 | 6181.1546 | 24724.6182 |  |  | 15579.8964
XFEL.EU | SIMEX/MD | p3.16xlarge | 64 | 488 | 0 | 0.07 | 24.48 | 24 | 587.52 | 41.1264 | 15011.136 | 60044.544 |  |  | 540518.4
CERIC | Ptycho | r4.4xlarge | 16 | 122 |  | 1 | 5.6449 | 24 | 135.4774 | 135.4774 | 49449.2364 | 197796.9456 |  |  | 124639.1712
CERIC | Jupyter | x1.16xlarge | 64 | 976 |  | 20 | 1.0109 |  |  | 24.2611 | 8855.3088 | 35421.2352 |  |  | 0
ESS | SIMEX/DFT (WP5) | 2 x c5.18xlarge | 144 | 288 |  | 0.5 | 5.6692 |  |  | 68.0298 | 24830.8858 | 99323.543 |  |  | 0
ESS | SIMEX/Spinw (WP5) | c5.9xlarge | 36 | 72 | 0 | 0.5 | 1.4173 |  | 0 | 17.0075 | 6207.7214 | 24830.8858 |  |  | 0
ESS | SIMEX/McStas (WP5) | c5.18xlarge | 72 | 144 |  | 1 | 2.8346 |  |  | 68.0298 | 24830.8858 | 99323.543 |  |  | 0
ESS | WP4 (sans, refl, qens, powder) | p3.2xlarge | 8 | 61 |  | 20 | 2.5092
ESS | WP4 (ins, sxtal, img) | r4.4xlarge | [12 empty] | 1023016.77
|  |  | EUR/vCPU/h | EUR/Gb/h
|  | c5 | 0.039369 | 0.019685
|  | p3 | 0.3825 | 0.050164
|  | x1 | 0.088201 | 0.0010357 |  |  | Y1
|  | r4 | 0.06318 | 0.0082859 |  | 1.01 | 20200 | 40400 | 101000 | 202000 | 363600
[6 empty] | 5.64 | 5640 | 11280 | 22560 | 56400 | 95880
Note on K7: is this correct? how is column G accounted for? -Carsten Grote
Note on B15: This will be many small jobs. The service will just be more like a web-service that needs load-balancing. Some of the software can use gpu power. ---- do we consider load balancing somewhere in this proposal? -Thomas Rod

## WP partners
WP | Title | Lead | Co-Lead | Leader | Co-Leader
1 | Management | ESRF |  | Jordi (ESRF)
2 | Data Policy and Stewardship | ESRF | ESS | Andy (ESRF)
3 | Data Catalog Services | ESS | CERIC | Tobias *ESS)
4 | Data Analysis Services | XFEL | ILL | Hans (XFEL)
5 | Data Modelling and Simulation | XFEL |  | Carsten (XFEL)
6 | EOSC Integration | ILL | EGI | Jean Francois (ILL)
7 | Sustainibility | CERIC |  | Roberto (CERIC)
8 | User Training | ESS | ELI | Thomas (ESS) | Tamas (ELI)
9 | Outreach and Communication | CERIC |  | Nicoleta (CERIC)

## ELI budget
Please note: This sheet was added on 06/09/2018 by Jordi Bodera following feedback received from Serena about the Grant Agreement
Entity | Concept | Cost | Justification in Google spreadsheets | Content in submitted in Annex 1 Part B
ELI-DC | Travel | 94105 | Travels between partners + WP trips + within partner sites
ELI-DC | Purchases | 68500 | Certificate of financial statement, annual conference (non-travel items), conference fees, workshop organisation, open access publications |  | 92026.25 | 0.33783
ELI-DC | Personnel | 1170125 | 253 person-months at 55500 per year
| TOTAL | 1665912.5 | Including 25% overheads for purhases and travel
of which
IP-ASCR | WP3 personnel | 120250 |  | WP3 Data Catalog Services (26 person-months)
IP-ASCR | WP4 personnel | 78625 |  | WP4 Data Analysis Services (17 person-months)
IP-ASCR | WP6 personnel | 18500 |  | WP6 EOSC Integration (4 person-months)
IP-ASCR | WP8 personnel | 74000 |  | WP8 Staff and User Training (16 person-months)
| TOTAL | 291375
ELI-HU | WP3 personnel | 120250 |  | WP3 Data Catalog Services (26 person-months)
ELI-HU | WP4 personnel | 78625 |  | WP4 Data Analysis Services (17 person-months)
ELI-HU | WP5 personnel | 115625 |  | WP5 Virtual Neutron and X-ray Laboratory (25 person-months)
ELI-HU | WP6 personnel | 18500 |  | WP6 EOSC Integration (4 person-months)
ELI-HU | WP8 personnel | 74000 |  | WP8 Staff and User Training (16 person-months)
| TOTAL | 407000
IFIN-HH | WP3 personnel | 120250 |  | WP3 Data Catalog Services (26 person-months)
IFIN-HH | WP4 personnel | 78625 |  | WP4 Data Analysis Services (17 person-months)
IFIN-HH | WP6 personnel | 18500 |  | WP6 EOSC Integration (4 person-months)
IFIN-HH | WP8 personnel | 74000 |  | WP8 Staff and User Training (16 person-months)
| TOTAL | 291375
| Total ELI 3rd linked parties | 989750 |  | 214 person-months in total (78 in WP3, 51 in WP4, 25 in WP5, 12 in WP6 and 48 in WP8
| TOTAL personnel remains | 180375 |  | Missing 39 person-months (3 in WP1, 20 in WP2, -1 in WP4, -1 in WP5, 12 in WP7, 6 in WP9)
Possible way to split 23 526.25 among the three 3rd linked parties
Concept |  |  | Cost
Travel to visit other consortium partners that contribute to the same work packages |  |  | 10986.25
Travel to other linked 3rd parties and ELI-DC to ensure good coordination within ELI |  |  | 8800
Travel to conferences |  |  | 3740
TOTAL |  |  | 23526.25

## PaNDaaS budget
PaNDaaS work package matrix (in p-month)
| Part. # |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21
WP | Task title |  | ESRF | ALBA | CYI | DESY | DLS | ELI-ALPS | ELETTRA | ENTROUV | ESS | EXACT | E-XFEL | HZB | ILL | KIT | MAX-IV | PSI | SESAME | SLAC | SOLEIL | SNS | STFC
Partner description
Commitment Letter | bar: 2 to 7; 9 to 17; 19; 21
1 - Management |  | Total WP
T1 | Project Management | 48 | 1: 48
T2 | Com & Interaction Commission | 2 | 1: 2
T3 | Mgt. Internal Communication | 2 | 1: 2
T4 | Mgt. Meetings | 2 | 1: 2
T5 | Mgt. Project Reporting | 2 | 1: 2
| Sub-total | 56 | 1: 56
2- Dis & Outreach
T1 | Overall Coordination | 13.5 | 3.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
T2 | Public Web Site | 1 | bar: 1
T3 | Scientific Articles, dissemination material | 2 | 1: 2
T4 | Participation in events | 1 | bar: 1
T5 | Organisation topical workshops | 10 | 1: 1.5; 2: 1.5; 4: 1.5; 7: 1.5; 16: 1.5; 17: 1.5; 21: 1.5
T6 | Establish links | 1 | bar: 1
T7 | Articles in periodic newsletters | 3 | 1: 3
T8 | Production of posters | 1 | bar: 1
| Sub-total | 33 | 14 | 2 | 0.5 | 2 | 0.5 | 0.5 | 2 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 2 | 2 | 0.5 | 0.5 | 0.5 | 2
3 - Health & LS UCs
T1 | Select softw. for Structural Biology | 12 | 5: 6; 12: 6
T2 | Select softw. for Serial Crystallography | 6 | 1: 6
T3 | Select softw. for optimised phase contrast imaging | 6 | 4: 6
T4 | Select softw. for BioSAXS (Molecular Dynamics) | 6 | 19: 6
T5 | Select softw. for Cellular Soft X-Rays | 6 | 2: 6
T6 | Select softw. for 2D crystal FEL diffraction analysis | 6 | 11: 6
T7 | Select softw. for XFEL CrystFEL | 6 | 11: 6
T8 | Service & Service Verification 1 | 21 | 1: 3; 2: 3; 4: 3; 5: 3; 11: 3; 12: 3; 19: 3
T9 | Service & Service Verification 2 | 21 | 1: 3; 2: 3; 4: 3; 5: 3; 11: 3; 12: 3; 19: 3
T10 | Service & Service Verification 3 | 21 | 1: 3; 2: 3; 4: 3; 5: 3; 11: 3; 12: 3; 19: 3
T11 | Service & Service Verification 4 | 21 | 1: 3; 2: 3; 4: 3; 5: 3; 11: 3; 12: 3; 19: 3
| Sub-total | 132 | 1: 18; 2: 18; 4: 18; 5: 18; 11: 24; 12: 18; 19: 18
4 - Materials Science UCs
T1 | Select softw. for Single cryst. neutron scat | 6 | 13: 6
T2 | Select softw. for absorption and emission spectrocopy | 6 | 16: 6
T3 | Select softw. for resonant diffraction pump-probe data | 6 | 7: 6
T4 | Select softw. for gisaxs | 6 | 4: 6
T5 | Select softw. for SANS and SAXS | 6 | 9: 6
T6 | Select softw. for spectroscopy | 8 | 4: 2; 15: 6
T7 | Service & Service Verification 1 | 21 | 4: 3; 7: 3; 9: 3; 13: 3; 15: 3; 16: 3; 17: 3
T8 | Service & Service Verification 2 | 21 | 4: 3; 7: 3; 9: 3; 13: 3; 15: 3; 16: 3; 17: 3
T9 | Service & Service Verification 3 | 21 | 4: 3; 7: 3; 9: 3; 13: 3; 15: 3; 16: 3; 17: 3
T10 | Service & Service Verification 4 | 21 | 4: 3; 7: 3; 9: 3; 13: 3; 15: 3; 16: 3; 17: 3
| Sub-total | 122 | 4: 20; 7: 18; 9: 18; 13: 18; 15: 18; 16: 18; 17: 12
5 - Industrial UCs
T1 | Select softw. for Nanoelectronics | 6 | 1: 6
T2 | Select softw. for Nanotomography | 6 | 1: 6
T3 | Select softw. for Catalysis | 6 | 5: 6
T4 | Select softw. for pharmaceuticals | 6 | 2: 6
T5 | Select softw. for neutron protein crystallography | 6 | 9: 6
T6 | Select softw. For strain-stress automatic proc. | 12 | 1: 6; 2: 6
T7 | Select softw. for Nuclear and particle physics | 6 | 13: 6
T8 | Select softw for quantum magnetism + fields | 6 | 21: 6
T9 | Service & Service Verification 1 | 18 | 1: 3; 2: 3; 5: 3; 9: 3; 13: 3; 21: 3
T10 | Service & Service Verification 2 | 18 | 1: 3; 2: 3; 5: 3; 9: 3; 13: 3; 21: 3
T11 | Service & Service Verification 3 | 18 | 1: 3; 2: 3; 5: 3; 9: 3; 13: 3; 21: 3
T12 | Service & Service Verification 4 | 18 | 1: 3; 2: 3; 5: 3; 9: 3; 13: 3; 21: 3
| Sub-total | 126 | 1: 30; 2: 24; 5: 18; 9: 18; 13: 18; 21: 18
6 - Architecture and Ref Impl.
T1 | Define minimum set of functionalities | 18 | 1: 2; 3: 1; 4: 2; 6: 3; 8: 1; 12: 2; 13: 4; 21: 3
T2 | Select cloud platform | 24 | 1: 6; 3: 3; 4: 2; 6: 3; 10: 1; 12: 2; 13: 3; 14: 2; 21: 2
T3 | Review and select hybrid cloud API layers | 21 | 1: 3; 3: 4; 4: 2; 8: 1; 13: 4; 15: 3; 21: 4
T4 | Edit technical reference implementation manual | 8 | 3: 5; 13: 1; 15: 2
T5 | Implement basic architecture in all RIs | 78 | 3 | 3 | 3 | 3 | 3 | 3 | 3 |  | 3 | 27 | 3 | 3 | 3 | 3 | 3 | 3 | 3 |  | 3 |  | 3
T6 | Development User access web portal | 47 | 2: 12; 6: 6; 8: 1; 12: 4; 13: 14; 21: 10
T7 | Evaluate and implement Remote Desktop solution | 19 | 1: 5; 4: 6; 12: 6; 13: 2
T8 | Common Monitoring and accounting tools | 16 | 1: 4; 13: 8; 21: 4
T9 | System Image configuration, deployment | 33 | 3: 5; 10: 16; 12: 6; 13: 3; 21: 3
| Sub-total | 264 | 23 | 15 | 21 | 15 | 3 | 15 | 3 | 3 | 3 | 44 | 3 | 23 | 42 | 5 | 8 | 3 | 3 |  | 3 |  | 29
7 - Common Tools
T1 | Enabling access with Umbrella ID | 62 | 4: 3; 5: 6; 8: 28; 13: 12; 15: 3; 16: 10
T2 | LOA & Authorisation | 24 | 5: 6; 8: 12; 13: 6
T3 | Service catalogue | 26 | 3: 6; 6: 5; 13: 3; 21: 12
T4 | Data movement service | 51 | 3: 4; 4: 12; 6: 5; 7: 12; 13: 6; 15: 12
T5 | Other cloud infrastructures | 22 | 3: 4; 4: 6; 21: 12
T6 | Cloud security | 24 | 8: 12; 13: 6; 21: 6
| Sub-total | 209 | 3: 14; 4: 21; 5: 12; 6: 10; 7: 12; 8: 52; 13: 33; 15: 15; 16: 10; 21: 30
8 - Online
T1 | Data streaming architecture | 82 | 1: 6; 4: 10; 6: 20; 16: 46
T2 | Optimized reduction/analysis algorithms | 46 | 3: 12; 4: 18; 6: 10; 16: 6
T3 | Workflow control and configuration | 48 | 5: 6; 6: 6; 9: 12; 13: 12; 16: 6; 19: 6
T4 | External tools integration | 42 | 1: 6; 2: 6; 7: 12; 13: 6; 16: 6; 21: 6
| Sub-total | 218 | 1: 12; 2: 6; 3: 12; 4: 28; 5: 6; 6: 36; 7: 12; 9: 12; 13: 18; 16: 64; 19: 6; 21: 6
9 - Data Access and Visualisation and Workflow
T1 | Data access | 67 | 1: 12; 2: 8; 5: 20; 13: 6; 15: 12; 17: 3; 21: 6
T2 | Data browsers | 35 | 1: 6; 2: 8; 5: 6; 7: 6; 17: 3; 21: 6
T3 | Data caching | 20 | 5: 2; 6: 12; 14: 6
T4 | Volume rendering | 38 | 2: 8; 6: 12; 14: 18
T5 | Analysis workflows | 60 | 1: 18; 5: 6; 11: 18; 19: 12; 21: 6
T6 | Workflow preservation | 52 | 5: 6; 11: 10; 13: 12; 19: 12; 21: 12
| Sub-total | 272 | 36 | 24 |  |  | 40 | 24 | 6 |  |  |  | 28 |  | 18 | 24 | 12 | 0 | 6 |  | 24 |  | 30
10 - User support tools & training
T1 | Community portal | 11 | 3: 3; 17: 8
T2 | Coordinate and edit technical documentation | 8 | 3: 5; 4: 3
T3 | User training | 10 | 3: 5; 17: 5
T4 | Programmer training | 28 | 3: 5; 14: 18; 17: 5
T5 | Setup and run helpdesk | 29 | 3: 24; 4: 3; 17: 2
| Sub-total | 86 | 3: 42; 4: 6; 14: 18; 17: 20
11 - Business Model & Sustainab.
T1 | Data management plan | 4 | bar: 1 to 4
T2 | Market analysis and segmentation | 4 | 2: 2; 12: 1; 15: 1
T3 | Financial plans, cloud and data preservation | 8 | 1: 1; 2: 1; 12: 1; 13: 4; 21: 1
T4 | Service management/strategy/design | 8 | 2: 4; 15: 4
T5 | Externalise | 4 | 19: 2; 21: 2
T6 | Federation | 7 | 1: 2; 2: 2; 7: 2; 13: 1
| Sub-total | 35 | 1: 4; 2: 10; 3: 1; 4: 1; 7: 2; 12: 2; 13: 5; 15: 5; 19: 2; 21: 3
| PM Total WPs | 1553 | 193 | 99 | 90.5 | 111 | 97.5 | 85.5 | 55 | 55.5 | 51.5 | 44.5 | 55.5 | 43.5 | 152.5 | 47.5 | 58.5 | 97 | 43 | 0.5 | 53.5 | 0.5 | 118
| PY Total WPs | 129.4167 | 16.0833 | 8.25 | 7.5417 | 9.25 | 8.125 | 7.125 | 4.5833 | 4.625 | 4.2917 | 3.7083 | 4.625 | 3.625 | 12.7083 | 3.9583 | 4.875 | 8.0833 | 3.5833 | 0.041667 | 4.4583 | 0.041667 | 9.8333
| Average yearly staff cost |  | 85 | 69 | 55 | 79 | 76 | 70 | 75 | 90 | 90 | 50 | 79 | 84 | 85 | 83 | 90 | 96 | 35 | 80 | 75 | 80 | 85
| Total in k€ (without overhead) | 10125.4583 | 1367.0833 | 569.25 | 414.7917 | 730.75 | 617.5 | 498.75 | 343.75 | 416.25 | 386.25 | 185.4167 | 365.375 | 304.5 | 1080.2083 | 328.5417 | 438.75 | 776 | 125.4167 | 3.3333 | 334.375 | 3.3333 | 835.8333
| Travel cost | 666 | 36 | 27 | 45 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 45 | 54 | 27 | 54 | 27
| Total in k€ (+25% overhead, without non-funded partners) | 12342.2396 | 1753.8542 | 745.3125 | 574.7396 | 947.1875 | 805.625 | 657.1875 | 463.4375 | 554.0625 | 516.5625 | 265.5208 | 490.4688 | 414.375 | 1384.0104 | 444.4271 | 582.1875 | 0 | 213.0208 | 0 | 451.7188 | 0 | 1078.5417
| in % of total funded | 100 | 14.2102 | 6.0387 | 4.6567 | 7.6744 | 6.5274 | 5.3247 | 3.7549 | 4.4892 | 4.1853 | 2.1513 | 3.9739 | 3.3574 | 11.2136 | 3.6009 | 4.717 | 0 | 1.7259 | 0 | 3.6599 | 0 | 8.7386
| in % of total project | 100 | 13.5014 | 5.622 | 4.0965 | 7.217 | 6.0985 | 4.9257 | 3.3949 | 4.1109 | 3.8146 | 1.8312 | 3.6085 | 3.0073 | 10.6682 | 3.2447 | 4.3331 | 7.6639 | 1.2386 | 0.03292 | 3.3023 | 0.03292 | 8.2548
| Subcontracting/PSI Swiss funding/USA |  | 1: 104; 16: 1003.75; 18: 57.3333; 20: 57.3333
Travel cost reasoning: | I average trip = 600€. 3*5 for annual meetings, 3x10 trips for WP coordination = 45 * 600 = 27k€ for a standard partner
ESRF + 15 trips for coordination activities = 24k€
CYI + SESAME = 1000 € per trip = 45k€
| Management + Policies | 91
| Outreach + Dissemination | 33
| Data analysis services | 380
| Research and technical development | 1049
1553

## Gantt
[5 empty] | Year 1 | [11 empty] | Year 2 | [11 empty] | Year 3 | [11 empty] | Year 4
Work Package | Id | Task Name | Start | End | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48
WP1 Management | T1.1 | Creation of PID and Executive Committee | 1 | 2
| T1.2 | Project Management and coordination | 1 | 48
| T1.3 | Administration and local coordination | 1 | 48
WP2 Data Policy and Stewardship | T2.1 | Lesson learned and FAI Definitions | 1 | 6
| T2.2 | Update PaNOSC data policy framework | 6 | 18
| T2.3 | Aprove Data Policy framework | 9 | 36
| T2.4 | Create Guidelines | 1 | 24
| T2.5 | Implement DMP template | 12 | 36
| T2.6 | Validation of Data Policy implementation | 12 | 36
WP3 Data Catalog Services | T3.1 | Develop API | 1 | 28
| T3.2 | Provisioning Federated search | 8 | 20
| T3.3 | Local Deployment | 20 | 44
| T3.4 | Catalog integration | 12 | 48
| T3.5 | Meta Anthology for Catalogues | 1 | 42
WP4 Data Analysis Services | T4.1 | Survey | 1 | 12
| T4.2 | Remote Desktop based analysis services | 1 | 36
| T4.3 | EOSC integration and common portal | 13 | 48
| T4.4 | Jupyter based analysis services | 1 | 48
| T4.5 | Deployment | 13 | 48
| T4.6 | Demonstrator | 37 | 48
WP5 Virtual Neutron and X-ray Laboratory | T5.1 | Simulation Infrastructure | 1 | 48
| T5.2 | Source simulation services | 1 | 24
| T5.3 | Beamline simulation services | 13 | 36
| T5.4 | Signal generation simulation | 25 | 48
| T5.5 | Simulation data workflows | 37 | 48
WP6 EOSC Integration | T6.1 | Management of the integration with e-Infrastructures | 1 | 48
| T6.2 | EOSC Hub Service Catalogue | 1 | 48
| T6.3 | Data availability for services | 1 | 48
| T6.4 | AAI Integration | 1 | 36
| T6.5 | Services Support | 12 | 48
| T6.6 | PaN Software Catalogue | 12 | 36
| T6.7 | Data archiving pilot | 12 | 48
| T6.8 | Procure commercial cloud | 30 | 42
WP7 Sustainibility | T7.1 | Stakeholder definition | 1 | 48
| T7.2 | Metrics and costs | 9 | 36
| T7.3 | Business models | 13 | 42
| T7.4 | Sustainability plan | 19 | 48
Staff training in data stewardship | T8.1 | Sustainability and maintainability | 4 | 15
| T8.2 | Integrate Jupyter technology | 19 | 30
| T8.3 | Integrate ESFRIs | 25 | 36
| T8.4 | Staff training in e-learning platform | 13 | 42
| T8.5 | Staff training in data stewardship | 25 | 32
| T8.6 | Training materials to foster the uptake of PaNOSC services | 31 | 42
| T8.7 | Introductory course to materials science | 31 | 42
| T8.8 | PaNOSC schools for students | 42 | 48
WP9 Outreach &Communication | T9.1 | Internal and external communication | 1 | 48
| T9.2 | Dissemination of results | 13 | 48
| T9.3 | Collaboration actions with other clusters | 1 | 48
MS1.1 Project Initiation Stage Completed
MS1.2 First Annual Workshop
MS1.3 Second Annual Workshop
MS1.4 Third Annual Workshop
MS1.5 Final Workshop
MS2.1 First version of PaNOSC policy framework
MS7.1 First Stakeholder Assembly
MS7.2 Second Stakeholder Assembly
MS7.3 Final Sustainability Plan
MS2.3 Implementation of PaNOSC DP framework
MS3.1 Anthology Feedback to API tasks
MS3.3 Catalogue Integration Best Practices meeting
M4.1 Prototype data analysis services completed
M2 Data analysis services accessible through EOSC
5.2 Demonstration of simulation services
5.1 Simulation codes in PaNData Software Catalog
5.4 Validation of simulation services
MS 6.1 Implementation of AAI integration at the level of the Identity providers
M2 PaNOSC services fully usable through the EOSC catalogue
MS8.4 e-learning platform workshop held
MS8.5 Training materials are available
M9.1 PaNOSC’s Website Ready
PROJECT INITIATION
PROJECT FINAL STAGE
PROJECT 1st STAGE
PROJECT 2nd STAGE
PROJECT 3rd STAGE