## Slide 1: WP1 – Management Report for Review Meeting
16th June, 2020
Author: Jordi Bodera

## Slide 2
WP1 – Management Report for Review Meeting
Objectives
Manage and coordinate the project to ensure that the objectives are delivered on time.  So far PaNOSC is delivering on time
Organise regular follow-up meetings and annual workshops  WPs are having regular meetings (minutes available in GitHub)  Project Management Committee for coordination  Kick-off meeting in Grenoble, 1st Annual meeting in Trieste, 2nd upcoming meeting in Prague
Manage change and risk  Following-up progress and comparing with forecasts  Implementation of risk management process
Interact with and follow-up all other work packages  Attending some other WP meetings  Internal milestones  Follow-up during Project Management Committee meetings

## Slide 3
WP1 – Management Report for Review Meeting
Tasks
T1.1 Creation of Project Initiation Documentation (M1-M2)  Documentation created on time and available in GitHub
appointment of Executive Committee  Body appointed with regular meetings to steer the project
and selection of the tools to be used for project management  GitHub with agreed arborescence structure  Mailing lists and Slack for internal communication  Google Docs for multiple editing
T1.2 Project management and coordination (M1-M48)  Regular meetings, email exchanges and general follow-up of the project
 Introduction of Key Performance Indicators (KPIs) and issue tracking
T1.3 Administration (M1-M48)  Management of mailing lists, minutes of meetings and other administrative tasks

## Slide 4
WP1 – Management Report for Review Meeting
Deliverables
D1.1 Project Initiation Documentation (M2)
D1.2 Data Management Plan (M6)
D1.3+ Mid-year summaries (M6, M18, M30, M42)
D1.4+ Report of annual workshop (M12, M24, M36, M48)
 So far all submitted
Milestones
MS1 Project initiation stage completed (M2)
MS2 Annual report submitted (M12, M24, M36, M48)
 So far all achieved

## Slide 5
WP1 – Management Report for Review Meeting
Management Structure
The management structure defined in the proposal and refined in the Project Initiation Documentation has been put in place, with all partners collaborating
No project administrator has been hired to support the work of the Project Coordinator and Project Manager though.

## Slide 6
WP1 – Management Report for Review Meeting
Risk Management
Is being applied as per the proposal, with ownership of risks delegated to PaNOSC members closer to the risk.
Issue Management
Important issues that cannot be dealt at WP level are documented in GitHub and discussed during the regular Project Management Committee Meetings.
Internal Communication
Mailing lists, Slack, PaNOSC calendar and regular meetings used.

## Slide 7
WP1 – Management Report for Review Meeting
Other management aspects
Management by exception,
letting WP leaders be independent and autonomous while encouraging collaboration between WPs and with other projects (like ExPaNDS)
Reminding WP leaders and PaNOSC partners representatives of major upcoming actions, reports, deliverables and milestones
Proactive approach to project management
    Regular meetings to follow-up progress
    Internal Milestones
    Internal Financial Report
    New KPIs being introduced
  Being open with the management data (all non-confidential items are available in GitHub)

## Slide 8
WP1 – Management Report for Review Meeting
Next steps
Submit Periodic Report
Grant Agreement modifications
    ELI-DC transformation into ELI-ERIC
    Transfer funds into subcontracting
  2nd PaNOSC annual meeting (joint with ExPaNDS)
  Continue regular meetings and following-up the project

## Slide 9: Thank you
Jordi.bodera@esrf.fr