## Slide 1: WP1 – Management Report for Review Meeting
16th June, 2020
Author: Jordi Bodera

## Slide 2
Table of contents
Objectives, Tasks, Deliverables and Milestones
Management structure
Grant Agreement modifications
Internal communication, Risk, Issue and other management aspects

## Slide 3
Objectives
Manage and coordinate the project to ensure that the objectives are delivered on time.
Organise regular follow-up meetings and annual workshops
Manage change and risk
Interact with and follow-up all other work packages
 So far PaNOSC is delivering on time
 WPs are having regular meetings (minutes available in GitHub)  Project Management Committee for coordination  Kick-off meeting in Grenoble, 1st Annual meeting in Trieste, 2nd upcoming meeting in Prague
 Following-up progress and comparing with forecasts  Implementation of risk management process
 Attending some other WP meetings  Internal milestones  Follow-up during Project Management Committee meetings

## Slide 4
Tasks
T1.1 Creation of Project Initiation Documentation (M1-M2)  Documentation created on time and available in GitHub
appointment of Executive Committee  Body appointed with regular meetings to steer the project
and selection of the tools to be used for project management  GitHub with agreed arborescence structure  Mailing lists and Slack for internal communication  Google Docs for multiple editing
T1.2 Project management and coordination (M1-M48)  Consortium Agreement  Regular meetings, email exchanges and general follow-up of the project
 Introduction of Key Performance Indicators (KPIs) and issue tracking
T1.3 Administration (M1-M48)  Management of mailing lists, minutes of meetings and other administrative tasks

## Slide 5
Deliverables & Milestones
Deliverables
D1.1 Project Initiation Documentation (M2)
D1.2 Data Management Plan (M6)
D1.3+ Mid-year summaries (M6, M18, M30, M42)
D1.4+ Report of annual workshop (M12, M24, M36, M48)
Milestones
MS1 Project initiation stage completed (M2)
MS2 Annual report submitted (M12, M24, M36, M48)
 So far all submitted
 So far all achieved

## Slide 6
Management Structure
The management structure defined in the proposal and refined in the Project Initiation Documentation has been put in place, with all partners collaborating
Regular meetings of the Project Management Committee (WP leaders + representatives from all partners) taking place every other week.

## Slide 7
Grant Agreement modifications
  ELI-DC transformation into ELI-ERIC
    As planned and stated in the Grant Agreement
      ELI-ERIC to replace ELI-DC as beneficiary
    ELI-ERIC to accept all assets and liabilities of ELI-DC
    ELI-BL and ELI-ALPS will be founding members of ELI-ERIC
    ELI-NP will not be a member of ELI-ERIC
  Transfer/ reallocation of funds from direct personnel costs
    Due to difficulties recruiting
    Internal financial report at M9 showed underspending
    Estimated total amount to be analysed following financial reporting at M18

## Slide 8
Spending
At month 9, an internal financial report was produced, which showed some under-spending compared with our forecasts:
A complete financial report as of month 18 could not be produced in time for this review meeting, however we expect:
Increase in spending
But not enough to catch-up with target spending levels
Increased gap between spending and forecast spending

## Slide 9
Other management aspects (1)
Risk Management
Is being applied as per the proposal, with ownership of risks delegated to PaNOSC members closer to the risk.
Issue Management
Important issues that cannot be dealt at WP level are documented in GitHub and discussed during the regular Project Management Committee Meetings.
Internal Communication
Mailing lists, Slack, PaNOSC calendar and regular meetings used. Also, regular meetings with ExPaNDS

## Slide 10
Other management aspects (2)
Management by exception,
letting WP leaders be independent and autonomous while encouraging collaboration between WPs and with other projects (like ExPaNDS)
Reminding WP leaders and PaNOSC partners representatives of major upcoming actions, reports, deliverables and milestones
Proactive approach to project management
    Regular meetings to follow-up progress
    Internal Milestones
    Internal Financial Report
    New KPIs being introduced (at WP level)
  Being open with the management data (all non-confidential items are available in GitHub)

## Slide 11
Next steps
Submit Periodic Report
Grant Agreement modifications
    ELI-DC transformation into ELI-ERIC
    Transfer funds into subcontracting
  2nd PaNOSC annual meeting (joint with ExPaNDS)
  Continue regular meetings and following-up the project

## Slide 12: Thank you
Jordi.bodera@esrf.fr

## Slide 13
Risks
  We follow a standard Risk Management methodology:
  Assessing risks based on likelihood and impact
  Nominating risk owners
  25 risks identified (11 medium, 14 low), among them:
    Staff shortages
    EOSC delays / structure

## Slide 14
Medium Risks
Name / Description | Comments
Low Engagement of partners in project | Constant monitoring required
Common Data Policy NOT possible | No problems in this area, however some partners are still to adopt a data policy
Data Catalog not integrated with data sources | No problems in this area, however some partners have not yet produced data or have a data policy in place
Duplication of efforts | All WPs actively ready to reuse open-source initiatives rather than re-inventing the wheel
Lack of staff | This is affecting some partners for a particular WP
Deliverables not met | No problems in this area and no indication that may happen
Data formats not compatible with simulation data | Ongoing work to ensure simulated data is interoperable with data analysis.
EOSC Core Services implementation delays | This could reduce the amount of time left at PaNOSC to integrate with these EOSC Core Services
Not clear definition of the EOSC structure | PaNOSC is involved in EOSC and collaborating, however EOSC final structure is yet being defined.
Development of unsustainable business models | Taking all measures to keep this risk under control
Not common viewpoint of stakeholders | This risk has not manifested yet, may become relevant later in the project.

## Slide 15
Low Risks
Name / Description | Comments
Executive Committee deadlock | No problems in this area and no indication that may happen
Staff Unavailability (staff leaving, illness, etc.) | Several cases have taken place as expected in a large project
Data Policy lack of compliance | Too early, data Policy Framework just released
Catalogue API lack of compliance | Too early, API to be fully implemented
APIs not compatible with data analysis framework | No problems in this area and no indication that may happen
Compute resources not available for testing /demos | No problems in this area and no indication that may happen
Delay in staff recruitment | In some cases recruitment has not been possible so far
Not clear definition of the EOSC stakeholders | EOSC stakeholders for WP7 – Sustainability are clear
e-neutrons delays | No longer relevant, pan-learning.org online
WP4 deliverables to WP8 are not in due time | No problems in this area and no indication that may happen
WP5 deliverables to WP8 are not in due time | No problems in this area and no indication that may happen
Difficulty to ensure outreach to key audiences | No problems in this area and no indication that may happen
Risk not to successfully communicating results | Too early to say, no problems reported in this area
Difficulty managing communications due to the big variety of partners and clusters | No problems in this area and no indication that may happen

## Slide 16
Links
  Risks links: https://docs.google.com/spreadsheets/d/1gfh0SI8IvM61URcpv2_0FSs3QcOBOXKH/edit#gid=1974817186
  KPI links: https://docs.google.com/spreadsheets/d/1iivsvBrix4v6lmC2U3sOC6YEXFeY0JzXHTM9QQQZwiY/edit#gid=0