## Deliverables, Ethics, DMP, Othe
Deliverables, Ethics, DMP, Other Reports for Project 823852
Deliverables, Ethics, DMP, Other Reports
WP No | Del Rel. No | Del No | Title | Description | Lead Beneficiary | Nature | Dissemination Level | Est. Del. Date (annex I) | Rev. Due Date | Receipt Date | Approval Date | Status
WP1 | D1.1 | D1 | Project initiation documentation | This set of documentation will include an executive summary for the project, its governance (including rules to appoint Executive Committee members), scope, organisation, risk management strategy, communication strategy, list of stakeholders, the list of executive committee members, executive committee appointment rules and initial set of risks and issues identified. | ESRF | Report | Public | 31 Jan 2019 |  | 12 Feb 2019 | 12 Feb 2019 | Approved
WP1 | D1.2 | D2 | Data Management Plan | Data Management Plan following H2020 guidelines, reviewed and agreed to by all partners. | ESRF | ORDP: Open Research Data Pilot | Public | 31 May 2019 |  | 31 May 2019 |  | Submitted
WP1 | D1.3 | D3 | Mid-year summary 1 | This will consist of a summary of the regular video conferences that will take place as part of Task 1.2 Project management and coordination and it will include news from the partners about their progress and a snapshot of the current health of the project. | ESRF | Report | Public | 31 May 2019 |  | 29 May 2019 |  | Submitted
WP1 | D1.4 | D4 | Report of annual workshop 1 | Report will focus on the activities of the annual workshop, status of the project, summary of progress achieved during the year, residual risks, main changes to the project and a report from the Executive Committee. | ESRF | Report | Public | 30 Nov 2019 |  | 29 Nov 2019 |  | Submitted
WP1 | D1.5 | D5 | Mid-year summary 2 | This will consist of a summary of the regular video conferences that will take place as part of Task 1.2 Project management and coordination and it will include news from the partners about their progress and a snapshot of the current health of the project. | ESRF | Report | Public | 31 May 2020 |  |  |  | Pending
WP1 | D1.6 | D6 | Report of annual workshop 2 | Reports will focus on the activities of the annual workshop, status of the project, summary of progress achieved during the year, residual risks, main changes to the project and a report from the Executive Committee. | ESRF | Report | Public | 30 Nov 2020 |  |  |  | Pending
WP1 | D1.7 | D7 | Mid-year summary 3 | This will consist of a summary of the regular video conferences that will take place as part of Task 1.2 Project management and coordination and it will include news from the partners about their progress and a snapshot of the current health of the project. | ESRF | Report | Public | 31 May 2021 |  |  |  | Pending
WP1 | D1.8 | D8 | Report of annual workshop 3 | Report will focus on the activities of the annual workshop, status of the project, summary of progress achieved during the year, residual risks, main changes to the project and a report from the Executive Committee. | ESRF | Report | Public | 30 Nov 2021 |  |  |  | Pending
WP1 | D1.9 | D9 | Mid-year summary 4 | This will consist of a summary of the regular video conferences that will take place as part of Task 1.2 Project management and coordination and it will include news from the partners about their progress and a snapshot of the current health of the project. | ESRF | Report | Public | 31 May 2022 |  |  |  | Pending
WP1 | D1.10 | D10 | Report of annual workshop 4 | Report will focus on the activities of the annual workshop, status of the project, summary of progress achieved during the year, residual risks, main changes to the project and a report from the Executive Committee. | ESRF | Report | Public | 30 Nov 2022 |  |  |  | Pending
WP2 | D2.1 | D11 | PaNOSC data policy | PaNOSC data policy framework updated to take into account (1) the latest understanding of FAIR principles, (2) the experience of the ESRFI PaN partners who have adopted and implemented the PanData data policy, (3) feedback from the PaN community, and (4) EOSC requirements. | ESRF | Report | Public | 31 May 2020 |  |  |  | Pending
WP2 | D2.2 | D12 | DMP Template | Develop a Data Management Plan template for scientists applying for beam time at the ESFRI PaNs which is compatible with the implementation of the PaNOSC data policy at each site. | ESS | Report | Public | 30 Nov 2021 |  |  |  | Pending
WP2 | D2.3 | D13 | Guidelines on implementing Data Policy | Report describing best practices and guidelines on how to implement the PaNOSC data policy framework based on the experience from the PaNOSC partners. The guidelines will take into account the different communities and environments of the PaNOSC partners. | ESRF | Report | Public | 30 Nov 2020 |  |  |  | Pending
WP2 | D2.4 | D14 | Integration of the policy | The document will include documentation on progress in adopting or adapting existing data management policies to the PaNOSC data policy framework. This deliverable will be written in collaboration with ELI. | CERIC-ERIC | Report | Public | 30 Nov 2021 |  |  |  | Pending
WP3 | D3.1 | D15 | API definition | The deliverable consists of the interface definition of a web API that can be used to federate data from all the PaNOSC catalogues. This is the first tier of the PANOSC metadata search API that supports queries based on generic metadata terms included in, for example, OpenAIRE or DOIs. Consideration should be given to how this can be implemented at partner sites in their local metadata catalogues. An extension for rich domain specific metadata should be planned, but does not have to be fully defined at this point. | ESS | Report | Public | 31 May 2020 |  |  |  | Pending
WP3 | D3.2 | D16 | Demonstrator implementation | This deliverable describes the implementation of the API from D3.1 and will cover lessons learned, changes to the originally proposed API, domain specific extensions and a rollout plan for the remaining facilities. | ESS | Demonstrator | Public | 31 Mar 2021 |  |  |  | Pending
WP3 | D3.3 | D17 | Catalog service | The experience of implementing metadata catalogues and the local search APIs to the federated HUB is reported in this deliverable. The status report covers technical problems encountered as well as administrative hurdles in complying with the WP2 policy framework. | ESS | Websites, patents filling, etc. | Public | 31 Mar 2022 |  |  |  | Pending
WP3 | D3.4 | D18 | Implementation Report | This deliverable reports on the catalogue integration at heterogeneous and distributed facilities. | ESS | Report | Public | 31 Jul 2022 |  |  |  | Pending
WP3 | D3.5 | D19 | NeXus Metadata Schema | NeXus provides a community agreed standard for encoding data and metadata in file. PANOSC will work with the community In trying to find rich metadata definitions for all the experimental techniques partner institutions provide access to. That allows the definitions to be utilised in metadata searches. This deliverable reports on suggested additions, extensions or simplifications to NeXus and the acceptance status or feedback from the community. | ESS | Report | Public | 31 May 2022 |  |  |  | Pending
WP4 | D4.1 | D20 | Report data analysis capture | This report should provide a global vision of technical and organisational elements needed for the provision of Data Analysis Services in the context of EOSC. For instance, it should allow to understand in detail the current data infrastructures of the partners, the different authentication and authorisation systems and their current technical solutions and workflow for providing software and data access. This report will then highlight the technologies that could be implemented to build on each existing infrastructure and create a harmonized solution. | ILL | Report | Public | 30 Nov 2019 |  | 29 Nov 2019 |  | Submitted
WP4 | D4.2 | D21 | Prototype remote desktop and Jupyter service | The 3 proposed services (VMs, remote desktop and Jupyter Notebooks) will be available as a remote service via internet. They both have been created and deployed at at least one partner site and serve as prototypes for the data analysis services. | ILL | Demonstrator | Confidential, only for members of the consortium (including the Commission Services) | 31 May 2020 |  |  |  | Pending
WP4 | D4.3 | D22 | Remote desktop and Jupyter analysis service deployed at EOSC | The remote desktop service and the Jupyter analysis services that were prototyped in D4.2 are fully implemented, offer a wider choice of data analysis procedures and make use of the work in WP6 making them available through the EOSC. This allows to carry out a range of relevant data analysis procedures remotely through a web interface, making use of EOSC services such as authentication, storage and compute allocation. | European XFEL | Demonstrator | Confidential, only for members of the consortium (including the Commission Services) | 31 May 2022 |  |  |  | Pending
WP4 | D4.4 | D23 | Publicly accessible Demonstrator | To demonstrate the value of the EOSC and the science carried out at the research infrastructures, we will make available typical data sets which are not under embargo (i.e open data). Special attention will be paid to provide data which allow students and new users to use the datasets in tutorials for learning different techniques. At the same time open data from user experiments will allow users to evaluate the advantages of cloud hosting of data analysis services. | CERIC-ERIC | Demonstrator | Public | 30 Nov 2022 |  |  |  | Pending
WP5 | D5.1 | D24 | Prototype simulation data formats | Documentation of domain specific extensions for openPMD for simulated radiation sources and target/sample trajectories developed in T5.1. Simulated detector signals will be stored in the NeXuS format. | ESS | Report | Public | 30 Nov 2019 |  | 29 Nov 2019 |  | Submitted
WP5 | D5.2 | D25 | Documented simulation APIs | Delivery of the harmonized simulation APIs developed in T5.1 as an open source software package accompanied by installation instructions and reference manual. | European XFEL | Other | Public | 30 Nov 2020 |  |  |  | Pending
WP5 | D5.3 | D26 | Documented simulation tasks executable | Publication of online repository hosting documented jupyter notebooks and Oasys canvases showcasing configuration, execution, and analysis of selected simulation tasks through the JupyterHub or remote desktop and utilizing the VINYL APIs. | ILL | Other | Public | 31 May 2022 |  |  |  | Pending
WP5 | D5.4 | D27 | Software tested and released including interactive simulation and analysis workflow | Updated release of tested and documented open source VINYL software package including integration into interactive data analysis workflow with feedback loop. Tests utilize validation datasets documented in Milestone MS5.4. | ESRF | Report | Public | 30 Nov 2022 |  |  |  | Pending
WP6 | D6.1 | D28 | Data-hub | This report should describe the technical integration of partners‘ data catalogues with the EGI DataHub solution for providing federated access to data. This will include technical documentation, constraints, if any, and evaluation. | ELI-DC | Report | Public | 31 May 2020 |  |  |  | Pending
WP6 | D6.2 | D29 | Compute cloud | This report will describe the technical work required to integrate partner compute resources into the EOSC environment. In particular, the security aspects and organisational challenges will be analyzed. | ELI-DC | Report | Public | 30 Nov 2021 |  |  |  | Pending
WP6 | D6.3 | D30 | AAI | The report will present the results of the feasibility study (Task 6.4) concerning the PaN AAI integration with EOSC and the result of the collaboration with GÉANT concerning the implementation. A demonstration of PaNOSC services with EOSC AAI will be presented. | ILL | Report | Public | 30 Nov 2021 |  |  |  | Pending
WP6 | D6.4 | D31 | Software catalogue | As a result of the work done in collaboration with the EOSC-hub project (Task 6.6), the integration of the PaNData software catalogue with the EOSC database catalogue will be firstly demonstrated by the selection of a set software that can meet the level of quality/service required by the EOSC database. | ILL | Demonstrator | Public | 30 Nov 2020 |  |  |  | Pending
WP6 | D6.5 | D32 | Report on EOSC integration | The deliverable will report on PaNOSC organizational, technical and strategic activities contributed to establish a PaNOSC data, application and services Commons. In particular, the deliverable will report on EOSC service management processes and the related performance, including incident management, data archiving and distributed computing in EOSC, and experience in cloud procurement and adoption. | ILL | Report | Public | 30 Nov 2022 |  |  |  | Pending
WP6 | D6.6 | D33 | Integration of RIs in EOSC | Plan, enable and support integration and provision of services from WP3, 4, 5 and 8 into the EOSC portfolio, with lead partner EGI. | EGI | Report | Public | 30 Nov 2022 |  |  |  | Pending
WP7 | D7.1 | D34 | Photon and Neutron EOSC Stakeholder Feedback | This report will include a list of stakeholders. Creation of links with the main players of the EOSC-hub, to the RDA and PaNdata community, ERF Data working group, and relevant industries in order to be able to collect input and feedback from them. The stakeholders will be involved in surveys during project execution in order to collect their important feedback. | CERIC-ERIC | Report | Public | 31 May 2020 |  |  |  | Pending
WP7 | D7.2 | D35 | Photon and Neutron EOSC metrics and costs model | Analysis and development of metrics for the evaluation of costs and metrics which demonstrate the added value of the services provided to the community. | CERIC-ERIC | Report | Public | 30 Nov 2021 |  |  |  | Pending
WP7 | D7.3 | D36 | Photon and Neutron EOSC Business model reference document | Development of advanced business and funding models in connection with Industrial Liaison Offices of each facility, the user communities and all the relevant industrial and research community EOSC stakeholders. | CERIC-ERIC | Report | Public | 31 May 2022 |  |  |  | Pending
WP7 | D7.4 | D37 | Photon and Neutron EOSC Sustainability plan | Based on the previous deliverable (D 7.1, D 7.2, D 7.3) we will develop of a formal long-term mission and vision for the sustainability of the PaNOSC infrastructure and software developed which will take into account the requirements of the different stakeholder and propose a sustainability strategy. | CERIC-ERIC | Report | Public | 30 Nov 2022 |  |  |  | Pending
WP8 | D8.1 | D38 | Report on lessons learned and future prospects for adopting best practises data stewardship at the PaNOSC facilities | Many technical and cultural barriers must be passed before best practise data stewardship is adopted at all involved facilities and it is important to learn from the past and the experiences gained during this work package. Therefore this report will discuss lessons-learned from the activities related to this topic in WP8 and what should or can be done in order to promote the adaptation of best practise data stewardship. | ELI-DC | Report | Public | 31 Jul 2021 |  |  |  | Pending
WP8 | D8.2 | D39 | Report on lessons learned for adopting the e-learning platform at the PaNOSC facilities, task 8.4 | The purpose of this report is to discuss and describe what did and did not work in order to improve the uptake of the e-learning platform in the future. | ELI-DC | Report | Public | 31 May 2022 |  |  |  | Pending
WP8 | D8.3 | D40 | Teaching material for users of PaNOSC services, FAIR principles, and the PaNOSC facilities accessible in the e-learning platform at pan-learning.org, task 8.5-7 | Teaching material developed in task 8.5-7 is accessible from pan-learning.org so that users can self-educate them on PaNOSC services, FAIR principles, and the PaNOSC facilities through pan-learning.org. | ESS | Websites, patents filling, etc. | Public | 31 May 2022 |  |  |  | Pending
WP8 | D8.4 | D41 | Closing report including report from summer school, task 8.8 | Write a report summarising the lessons-learned of the whole work package and with suggestions for future development and actions required for ensuring sustainability. The report should particularly summarize the lessons-learned from the final summer school (task 8.8) because that in itself wrasp up and exploits all activities in this work package. | ESS | Report | Public | 30 Nov 2022 |  |  |  | Pending
WP9 | D9.1 | D42 | PaNOSC’s Communication and Dissemination Plan | The document will contain the communication and dissemination strategy to be implemented throughout the project, and will include the actions and tools that will be carried out and deployed by the partners to engage project’s stakeholders, and to ensure the dissemination and foster the exploitation of the project’s outputs and results. | CERIC-ERIC | Report | Confidential, only for members of the consortium (including the Commission Services) | 30 Jun 2019 |  | 17 Sep 2019 |  | Submitted
WP9 | D9.2 | D43 | PaNOSC’s Website | The project’s website panosc.eu will provide all information about the project’s scope, objectives and actions, as well as news and access to resources like documentation, training material and source code repositories, and links to the catalogue services developed throughout the project. | CERIC-ERIC | Websites, patents filling, etc. | Public | 31 May 2019 |  | 31 May 2019 |  | Submitted
WP9 | D9.3 | D44 | PaNOSC’s repository for internal communications | The repository will be based on a remote file storage platform which will make available the project’s working documents and deliverables to all the partners. | CERIC-ERIC | Websites, patents filling, etc. | Confidential, only for members of the consortium (including the Commission Services) | 28 Feb 2019 |  | 28 Feb 2019 | 28 Feb 2019 | Approved
WP9 | D9.4 | D45 | Dissemination and Outreach activities | A report will be published at the end of the project of all dissemination actions, publications and outreach activities carried out throughout the project. Partners will regularly collect such data to monitor performance in reaching and engaging project’s stakeholders. | CERIC-ERIC | Websites, patents filling, etc. | Public | 30 Nov 2022 |  |  |  | Pending
WP10 | D10.1 | D46 | POPD - Requirement No. 1 | 4.1. The applicant must check if a declaration on compliance and/or authorisation is required under national law for collecting and processing personal data as described in the proposal. If yes, the declaration on compliance and/or authorisation must be kept on file. 4.2. If no declaration on compliance or authorisation is required under the applicable national law, a statement from the designated Data Protection Officer that all personal data collection and processing will be carried out according to EU and national legislation must be kept on file. 4.4. Detailed information on the procedures for data collection, storage, protection, retention, and destruction, and confirmation that they comply with national and EU legislation must be kept on file. 4.6. Detailed information on the informed consent procedures in regard to the collection, storage, and protection of personal data must be kept on file. 4.7. Templates of the informed consent forms and information sheets (in language and terms intelligible to the participants) must be kept on file. | ESRF | Ethics | Confidential, only for members of the consortium (including the Commission Services) | 31 Dec 2018 |  | 14 Jun 2019 |  | Submitted