## Slide 1: WP7 Sustainability
19th June, 2019
Author: Roberto Pugliese, Dario Roccella, CERIC-ERIC

## Slide 2: Participants / effort / critical aspects
The connection with the stakeholders and the collection of their feedback is a critical aspect of the work package.

## Slide 3: Tasks and deliverables

## Slide 4: Task 7.1 Stakeholders for the Photon and Neutron community EOSC [M1,18]
  MS 7.1 List of stakeholders 05/2019
  D 7.1 : Photon and Neutron EOSC Stakeholder Feedback (Report, 05/2020)
  Definition of a database of stakeholders.
    Google questionnaire to all partners -> Feb 2019
    Answers will be grouped to define categories of stakeholders ->March 2019
    Targeted questionnaires for every category of stakeholder will be developed and the questionnaires will be used as a base for the interviews.
  The feedback from stakeholders will allow us to address the other tasks

## Slide 5: Stakeholder database
Textual form:
  https://docs.google.com/document/d/1wUnVc0QkORbFQC8rkRykOP069UT0rJAlPw089ftsaKg/edit?usp=sharing
Spreadsheet form:
  https://docs.google.com/spreadsheets/d/1KLT3niIfvhGXsO6LcRKnJXHv9gdO-gZ6pncEJSagGWM/edit#gid=0

## Slide 6: Task 7.2 Metrics and cost for the Photon and Neutron community EOSC [M9-36]
  D 7.2 : Photon and Neutron EOSC metrics and costs model (Report, 11/2021)
  Analysis and development of metrics for the evaluation of costs and added value of the services provided to the community.
    Consultation with partners and other RIs that have already implemented some of the services -> Dec 2019
    Development of the first draft metrics, considering the feedback from stakeholders -> Dec 2020
    Refinement of the metrics, according to the recurrent stakeholders consultation and first implementations -> Oct 2021
    Final version of the metrics and cost model -> Nov 2021

## Slide 7: Task 7.3 Business models for Photon and Neutron EOSC [M13-42]
  D 7.3 : Photon and Neutron EOSC Business model reference document (Report, 05/2022)
  Development of advanced business and funding models in connection with Industrial Liaison Offices of each facility, the user communities and all the relevant industrial and research community EOSC stakeholders.
    Analysis of the consultation with stakeholders -> Jan 2020 [M14]
    Development of the first draft business model -> June 2021
    Refinement of the business model (according to stakeholders consultation and cost metrics model) and development of the funding model -> March 2022
    Final version of the business model reference document -> May 2022

## Slide 8: Task 7.4 Sustainability plan for the Photon and Neutron EOSC [M19-48]
  MS 7.2 Final Sustainability Plan
  D 7.4 : Photon and Neutron EOSC Sustainability plan (Report, 12/2022)
  Development of a formal long-term mission and vision for the sustainability of the PaNOSC infrastructure and software developed which will balance the viewpoints of the different stakeholder and the developed business models.
    Analysis of the consultation with stakeholders -> Jan 2020 [M20]
    Development of the outline of the sustainability plan -> June 2020
    Development of the contents based on the outcomes of the previous tasks, draft sustainability plan -> June 2022
    Final version of the sustainability plan -> Nov 2022

## Slide 9: Thank you
roberto.pugliese@elettra.eu