## Slide 1
WP 7 – Sustainability December 2018 - November 2022
Roberto Pugliese 15.01.2019
Photon and Neutron Open Science Cloud
Ornela De Giacomo – WP 7 Sustainability – 15.01.2019

## Slide 2
WP 7 – Sustainability
This project has received funding from the European Union's Horizon 2020 research and innovation programme under grant agreement No 823852
Roberto Pugliese– WP 7 Sustainability – 16.01.2019
Participants | PM
CERIC-ERIC | 32
ESRF | 3
ILL | 3
EU-XFEL | 3
ESS | 3
ELI-DC | 12
Tot. | 56
The connection with the stakeholders and the collection of their feedback is a critical aspect of the work package.

## Slide 3
WP 7 – Sustainability
This project has received funding from the European Union's Horizon 2020 research and innovation programme under grant agreement No 823852
Roberto Pugliese– WP 7 Sustainability – 16.01.2019
Task | Deliv | Due Date
Task 7.1 - Stakeholders for the Photon and Neutron community EOSC | D 7.1 | 05/2020
Task 7.2 - Metrics and cost for the Photon and Neutron community EOSC | D 7.2 | 11/2021
Task 7.3 - Business models for Photon and Neutron EOSC | D 7.3 | 05/2022
Task 7.4 - Sustainability plan for the Photon and Neutron EOSC | D 7.4 | 12/2022
Task | Deliv | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48
7.1 | D 7.1 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
7.2 | D 7.2 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
7.3 | D 7.3 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
7.4 | D 7.4 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | Dec -18 |  |  |  |  |  |  |  |  |  |  |  | Dec-19 |  |  |  |  |  |  |  |  |  |  |  | Dec-20 |  |  |  |  |  |  |  |  |  |  |  | Dec-21 |  |  |  |  |  |  |  |  |  |  | Nov-22 | 

## Slide 4
WP 7 – Sustainability
Task 7.1 Stakeholders for the Photon and Neutron community EOSC [M1,18]
  MS 7.1 List of stakeholders 05/2019
  D 7.1 : Photon and Neutron EOSC Stakeholder Feedback (Report, 05/2020)
Definition of a database of stakeholders.
  Google questionnaire to all partners -> Feb 2019
  Answers will be grouped to define categories of stakeholders ->March 2019
  Targeted questionnaires for every category of stakeholder will be developed and the questionnaires will be used as a base for the interviews.
  The feedback from stakeholders will allow us to address the following tasks
This project has received funding from the European Union's Horizon 2020 research and innovation programme under grant agreement No 823852
Roberto Pugliese– WP 7 Sustainability – 16.01.2019

## Slide 5
WP 9 – Stakeholders
  European PaN sources
PaNOSC partners and national PaN RIs
  PaN user community
  Community of RIs from other clusters
ENVRI-FAIR, EOSC-LIFE, ESCAPE, SSHOC
  e-infrastructures
EGI, Géant, OpenAIRE, PRACE, RDA Europe
  Pan European RIs
  Pan European RIs (ERICs, ESFRI)
  Researchers at large in both academia and industry
Beyond the PaN user community
  Other potential contributors to the EOSC
  EC, national authorities and funding agencies, policy makers
This project has received funding from the European Union's Horizon 2020 research and innovation programme under grant agreement No 823852
Roberto Pugliese– WP 7 Sustainability – 16.01.2019

## Slide 6
WP 7 – Sustainability
Task 7.2 Metrics and cost for the Photon and Neutron community EOSC
[M9-36]
  D 7.2 : Photon and Neutron EOSC metrics and costs model (Report, 11/2021)
Analysis and development of metrics for the evaluation of costs and added value of the services provided to the community.
  Consultation with partners and other RIs that have already implemented some of the services -> Dec 2019
  Development of the first draft metrics, considering the feedback from stakeholders -> Dec 2020
  Refinement of the metrics, according to the recurrent stakeholders consultation and first implementations -> Oct 2021
  Final version of the metrics and cost model -> Nov 2021
This project has received funding from the European Union's Horizon 2020 research and innovation programme under grant agreement No 823852
Roberto Pugliese– WP 7 Sustainability – 16.01.2019

## Slide 7
WP 7 – Sustainability
Task 7.3 Business models for Photon and Neutron EOSC [M13-42]
  D 7.3 : Photon and Neutron EOSC Business model reference document (Report, 05/2022)
Development of advanced business and funding models in connection with Industrial Liaison Offices of each facility, the user communities and all the relevant industrial and research community EOSC stakeholders.
Analysis of the consultation with stakeholders -> Jan 2020 [M14]
Development of the first draft business model, using the business model canvas or modification of this to define and reason upon the sustainable business models -> June 2021
Refinement of the business model (according to stakeholders consultation and cost metrics model) and development of the funding model -> March 2022
Final version of the business model reference document -> May 2022
This project has received funding from the European Union's Horizon 2020 research and innovation programme under grant agreement No 823852
Roberto Pugliese– WP 7 Sustainability – 16.01.2019

## Slide 8
WP 7 – Sustainability
Task 7.4 Sustainability plan for the Photon and Neutron EOSC [M19-48]
MS 7.2 Final Sustainability Plan
  D 7.4 : Photon and Neutron EOSC Sustainability plan (Report, 12/2022)
Development of a formal long-term mission and vision for the sustainability of the PaNOSC infrastructure and software developed which will balance the viewpoints of the different stakeholder and the developed business models.
Analysis of the consultation with stakeholders -> Jan 2020 [M20]
Development of the outline of the sustainability plan -> June 2020
Development of the contents based on the outcomes of the previous tasks, draft sustainability plan -> June 2022
Final version of the sustainability plan -> Nov 2022
This project has received funding from the European Union's Horizon 2020 research and innovation programme under grant agreement No 823852
Roberto Pugliese– WP 7 Sustainability – 16.01.2019

## Slide 9
WP 7 – Sustainability
THANK YOU
This project has received funding from the European Union's Horizon 2020 research and innovation programme under grant agreement No 823852
Roberto Pugliese– WP 7 Sustainability – 16.01.2019