## Risks
Information from the Proposal | [5 empty] | Information from Project stage
# | Risk Name | Risk Description | WP involved | Probability | Initial mitigation measure | New Probability | Impact | Assessment | Comments | Owner | Owner Comments | Due Date
1 | Low Engagement | Participants become less engaged in project | All WPs | Medium | Monthly video conferences tracking progress, actions and risks and frequent communication to keep all participants engaged. Interact with other EOSC projects to ensure motivation stays high. | Unlikely | Moderate | Medium
2 | Executive Committee deadlock | Executive Committee deadlock prevents decision making | All WPs | Low | The Executive Committee and its guidelines will be created in a way to prevent blockages. | Unlikely | Major | Medium
3 | Staff Unvailability | Key staff members become unavailable (staff leaving, illness, etc.) | All WPs | Medium | Minimise single points of failure among staff in the participants, ensure good communication and document work being done. | Very likely | Moderate | High
4 | Common Data Policy NOT possible | Local and/or legal conditions prevent a common data policy. | 2 | Low | All parties in the proposal have committed to an open data policy. Make a policy with minimal core and optional parts | Moderate | Moderate | Medium
5 | Data Policy lack of compliance | Data policy formally but not effectively accepted. The users may be forced to sign it but not fully comply with it (e.g. minimal metadata) | 2 | Medium | Adequate involvement of the user communities of each facility especially for heterogeneous and distributed facilities. | Moderate | Moderate | Medium
6 | Catalogue API lack of compliance | Some of the facilities will not be able to meet the mandatory requirements for catalogue API | 3 | Low | All parties have the source code of their metadata catalogues so they can adapt them. In case changes cannot be made allow exceptions to be granted. | Moderate | Moderate | Medium
7 | Data Catalog not integrated with data sources | Data Catalog not integrated with data sources | 3 | High | Adequate effort to integrate data sources (e.g. experimental stations) with the catalog has to be foreseen at least for highly distributed and heterogeneous facilities. | Moderate | Moderate | Medium
8 | Duplication | Duplication of efforts/branching of projects/lack of sustainability | 4 | Medium | Where we use open source and need to modify it to adopt to our needs, we aim to feed those changes back to the open source project. | Unlikely | Moderate | Medium
9 | Lack of staff | Lack of skilled staff | 4 | Low | We have relevant expertise at the facilities and can train new staff if required in most areas. Where this is not the case, we have risk-mitigation such as the co-operation with the Jupyter team. | Unlikely | Moderate | Medium
10 | Deliverables not met | Failure of partner to meet task or deliverable date | 5 | Low | Weekly teleconference meetings to monitor progress and update intermediate tasks. | Unlikely | Moderate | Medium
11 | Data formats not compatible | Data formats not published or not compatible with simulation data | 3,5 | Medium | Fall back on existing data formats (NeXus, CXIDB) and metadata standards (openPMD) | Unlikely | Moderate | Medium
12 | APIs not compatible | Developed APIs not compatible with data analysis framework | 4,5 | Medium | Monthly meeting with WP 4 contributors to address compatibility issues | Unlikely | Moderate | Medium
13 | Compute resources not available | Compute resources needed for testing and demonstrations not available or insufficient | 5 | High | Apply for HPC resources, e.g. | Moderate | Moderate | Medium
14 | Staff not recruited | Recruitment of skilled staff | 6 | Medium | PRACE preliminary access | Unlikely | Moderate | Medium
15 | EOSC delays | Difficulties due to the EOSC core services implementation delays | 6 | Medium | Start recruitment as early as possible. | Unlikely | Moderate | Medium
16 | Not clear definition of the EOSC structure | Not clear definition of the EOSC structure | 7 | Low | Close collaboration with the EOSC involved partners will allow issues early identification and response. | Unlikely | Moderate | Medium
17 | Not clear definition of the EOSC stakeholders | Not clear definition of the EOSC stakeholders | 7 | Low | Direct collaboration with the EOSC-hub to participate in the definition of the Hub (service management processes, activities, policies and its governance) together with main EOSC stakeholders (e.g. EGI, EUDAT, GÉANT, and other major research infrastructures from other disciplines) | Unlikely | Minor | Low
18 | Not common viewpoint | Not clear understanding and harmonisation of the stakeholders’ viewpoints | 7 | Medium | Stakeholder Feedback | Moderate | Minor | Medium
19 | Development of unsustainable business models | Development of unsustainable business models | 7 | High | Stakeholder Feedback | Moderate | Major | High
20 | e-neutrons delays | Delay in migrating e-neutrons.org to ESS | 8 | Low | Preparation of different versions of the Sustainability plan to match with stakeholder feedbacks . | Moderate | Minor | Medium
21 | WP4 deliverables to WP8 are not in due time | WP4 deliverables to WP8 are not in due time | 4,8 | Low | Migrate and setup software development infrastructure before starting to remove technical debt | Unlikely | Moderate | Medium
22 | WP5 deliverables to WP8 are not in due time | WP5 deliverables to WP8 are not in due time | 5,8 | Low | Make detailed plan (MS8.1) at start of project and subsequently update regularly (monthly) to ensure that WP4 deliverables to WP8 are delivered in due time | Unlikely | Moderate | Medium
23 | Difficulty to ensure outreach to key audiences | Difficulty to ensure outreach to key audiences | 9 | Low | Make detailed plan at start of project (MS8.2) that ensures that WP5 deliverables required for WP8 are delivered in due time and update the plan on a regular (monthly) basis. Focus effort on easily doable PaNOSC beneficiaries to ensure success for at least some of the PaNOSC beneficiaries. | Moderate | Moderate | Medium
24 | Risk not to successfully communicating results | Risk not to successfully communicating results | 9 | Medium | The project’s communications strategy will detail the target groups to be addressed, as well as the plan to make a mapping of key audiences at the beginning of and throughout the project | Unlikely | Moderate | Medium
25 |  | Difficulty managing communications due to the big variety of partners and clusters | 9 | Medium | The WP leader and the partnership will put efforts in keeping regular contacts with other clusters to ensure there is a complete and homogeneous communications of results. The yearly communication plans annexed to the strategy will include key actions and events of the community, to avoid double efforts, and to ensure that common objectives are met and main outcomes are communicated | Unlikely | Moderate | Medium
26 | [7 empty] | FALSE
27 | [7 empty] | FALSE
28 | [7 empty] | FALSE
29 | [7 empty] | FALSE
30 | [7 empty] | FALSE
31 | [7 empty] | FALSE
32 | [7 empty] | FALSE

## Drop down lists
Impact | Probability
Minor | Unlikely
Moderate | Moderate
Major | Very likely