## PaNOSC budget
|  |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7
|  |  | Total | ESRF | ILL | XFEL.EU | ESS | ELI | CERIC | EGI |  | Start month | End month | Length in months | start -1
WP1 Management | T1.1 | Creation of PID and Executive Committee |  | 2 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 2 | 2 | 0
| T1.2 | Project Management and coordination | 28 | 28 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 48 | 48 | 0
| T1.3 | Administration and local coordination | 34 | 19 | 3 | 3 | 3 | 3 | 3 | 0 |  | 1 | 48 | 48 | 0
|  | Sub-total | 64 | 49 | 3 | 3 | 3 | 3 | 3 | 0 | 4.621%
WP2 Data Policy and Stewardship
| T2.1 | Lesson learned and FAI Definitions | 6 | 1 | 1 | 0 | 1 | 1 | 2 | 0 |  | 1 | 6 | 6 | 0
| T2.2 | Update PaNOSC data policy framework | 8 | 2 | 1 | 1 | 2 | 1 | 1 | 0 |  | 6 | 18 | 13 | 5
| T2.3 | Aprove Data Policy framework | 12 | 1 | 1 | 1 | 1 | 6 | 2 | 0 |  | 9 | 36 | 28 | 8
| T2.4 | Create Guidelines | 20 | 9 | 1 | 1 | 4 | 3 | 2 | 0 |  | 1 | 24 | 24 | 0
| T2.5 | Implement DMP template | 22 | 2 | 6 | 0 | 6 | 6 | 2 | 0 |  | 12 | 36 | 25 | 11
| T2.6 | Validation of Data Policy implementation | 8 | 2 | 0 | 0 | 0 | 3 | 3 | 0 |  | 12 | 36 | 25 | 11
|  | Sub-total | 76 | 17 | 10 | 3 | 14 | 20 | 12 | 0 | 5.487%
WP3 Data Catalog Services | T3.1 | Develop API | 59 | 1 | 9 | 6 | 15 | 14 | 14 | 0 |  | 1 | 28 | 28 | 0
|  | merged with T3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 1 | -1
|  | merged with T3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 1 | -1
| T3.2 | Provisioning Federated search | 39 | 0 | 3 | 0 | 10 | 20 | 6 | 0 |  | 8 | 20 | 13 | 7
| T3.3 | Local Deployment | 36 | 6 | 6 | 6 | 6 | 6 | 6 | 0 |  | 20 | 44 | 25 | 19
| T3.4 | Catalog integration | 88 | 12 | 0 | 6 | 0 | 20 | 50 | 0 |  | 12 | 48 | 37 | 11
| T3.5 | Meta Anthology for Catalogues | 69 | 6 | 3 | 18 | 12 | 18 | 12 | 0 |  | 1 | 42 | 42 | 0
|  | Sub-total | 291 | 25 | 21 | 36 | 43 | 78 | 88 | 0 | 21.01%
WP4 Data Analysis Services | T4.1 | Survey | 9 | 1 | 3 | 2 | 1 | 1 | 1 | 0 |  | 1 | 12 | 12 | 0
| T4.2 | Remote Desktop based analysis services | 66 | 0 | 36 | 0 | 12 | 0 | 18 | 0 |  | 1 | 36 | 36 | 0
| T4.3 | EOSC integration and common portal | 39 | 6 | 6 | 2 | 6 | 6 | 13 | 0 |  | 13 | 48 | 36 | 12
| T4.4 | Jupyter based analysis services | 124 | 22 | 12 | 42 | 6 | 30 | 12 | 0 |  | 1 | 48 | 48 | 0
| T4.5 | Deployment | 60 | 6 | 12 | 12 | 6 | 12 | 12 | 0 |  | 13 | 48 | 36 | 12
| T4.6 | Demonstrator | 11 | 1 | 2 | 2 | 1 | 1 | 4 | 0 |  | 37 | 48 | 12 | 36
|  | Sub-total | 309 | 36 | 71 | 60 | 32 | 50 | 60 | 0 | 22.31%
WP5 Virtual Neutron and X-ray Laboratory | T5.1 | Simulation Infrastructure | 36 | 4 | 0 | 24 | 4 | 0 | 4 | 0 |  | 1 | 48 | 48 | 0
| T5.2 | Source simulation services | 40 | 20 | 0 | 2 | 0 | 9 | 9 | 0 |  | 1 | 24 | 24 | 0
| T5.3 | Beamline simulation services | 52 | 6 | 12 | 8 | 10 | 0 | 16 | 0 |  | 13 | 36 | 24 | 12
| T5.4 | Signal generation simulation | 53 | 0 | 12 | 8 | 13 | 15 | 5 | 0 |  | 25 | 48 | 24 | 24
| T5.5 | Simulation data workflows | 38 | 10 | 12 | 6 | 4 | 0 | 6 | 0 |  | 37 | 48 | 12 | 36
|  | Sub-total | 219 | 40 | 36 | 48 | 31 | 24 | 40 | 0 | 15.81%
WP6 EOSC Integration | T6.1 | Management of the integration with e-Infrastructures | 7 | 1 | 6 | 0 | 0 | 0 | 0 | 0 |  | 1 | 48 | 48 | 0
| T6.2 | EOSC Hub Service Catalogue | 16 | 6 | 2 | 2 | 2 | 2 | 2 | 0 |  | 1 | 48 | 48 | 0
| T6.3 | Data availability for services | 17 | 3 | 3 | 3 | 3 | 2 | 3 | 0 |  | 1 | 48 | 48 | 0
| T6.4 | AAI Integration | 19 | 2 | 9 | 2 | 2 | 2 | 2 | 0 |  | 1 | 36 | 36 | 0
| T6.5 | Services Support | 34 | 4 | 6 | 6 | 6 | 6 | 6 | 0 |  | 12 | 48 | 37 | 11
| T6.6 | PaN Software Catalogue | 16 | 4 | 12 | 0 | 0 | 0 | 0 | 0 |  | 12 | 36 | 25 | 11
| T6.7 | Data archiving pilot | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 12 | 48 | 37 | 11
| T6.8 | Procure commercial cloud | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 |  | 30 | 42 | 13 | 29
|  | Sub-total | 192 | 21 | 38 | 13 | 13 | 12 | 13 | 82 | 13.86%
WP7 Sustainibility | T7.1 | Stakeholder definition | 7 | 0 | 1 | 1 | 1 | 2 | 2 | 0 |  | 1 | 48 | 48 | 0
| T7.2 | Metrics and costs | 12 | 1 | 1 | 1 | 1 | 2 | 6 | 0 |  | 9 | 36 | 28 | 8
| T7.3 | Business models | 17 | 1 | 0 | 0 | 0 | 4 | 12 | 0 |  | 13 | 42 | 30 | 12
| T7.4 | Sustainability plan | 20 | 1 | 1 | 1 | 1 | 4 | 12 | 0 |  | 19 | 48 | 30 | 18
|  | Sub-total | 56 | 3 | 3 | 3 | 3 | 12 | 32 | 0 | 4.043%
Staff training in data stewardship | T8.1 | Sustainability and maintainability | 18 | 0 | 0 | 0 | 12 | 6 | 0 | 0 |  | 4 | 15 | 12 | 3
| T8.2 | Integrate Jupyter technology | 20 | 2 | 3 | 1 | 6 | 6 | 2 | 0 |  | 19 | 30 | 12 | 18
| T8.3 | Integrate ESFRIs | 15 |  |  |  | 3 | 12 | 0 | 0 |  | 25 | 36 | 12 | 24
| T8.4 | Staff training in e-learning platform | 12 | 1 | 1 | 1 | 4 | 4 | 1 | 0 |  | 13 | 42 | 30 | 12
| T8.5 | Staff training in data stewardship | 17 | 1 | 2 | 1 | 2 | 10 | 1 | 0 |  | 25 | 32 | 8 | 24
| T8.6 | Training materials to foster the uptake of PaNOSC services | 21 | 2 | 3 | 1 | 3 | 10 | 2 | 0 |  | 31 | 42 | 12 | 30
| T8.7 | Introductory course to materials science | 3 |  |  |  | 3 |  |  |  |  | 31 | 42 | 12 | 30
| T8.8 | PaNOSC schools for students | 2 |  |  |  | 2 |  |  |  |  | 42 | 48 | 7 | 41
|  | Sub-total | 108 | 6 | 9 | 4 | 35 | 48 | 6 | 0 | 7.798%
WP9 Outreach &Communication | T9.1 | Internal and external communication | 34 | 2 | 2 | 2 | 2 | 2 | 24 | 0 |  | 1 | 48 | 48 | 0
| T9.2 | Dissemination of results | 18 | 2 | 2 | 2 | 2 | 2 | 8 | 0 |  | 13 | 48 | 36 | 12
| T9.3 | Collaboration actions with other clusters | 18 | 2 | 2 | 2 | 2 | 2 | 8 | 0 |  | 1 | 48 | 48 | 0
|  | Sub-total | 70 | 6 | 6 | 6 | 6 | 6 | 40 | 0 | 5.054%
|  | Remaining Person Months |  | -15.1583 | 1.6665 | 0.354 | -6.4446 | 39.2448 | -0.37387 |  | Red if too high, Green otherwise
|  | PM Total WPs | 1385 | 203 | 197 | 176 | 180 | 253 | 294 | 82
|  | PY Total WPs | 115.4167 | 16.9167 | 16.4167 | 14.6667 | 15 | 21.0833 | 24.5 | 6.8333
|  | Average yearly staff cost (kEUR) |  | 85000 | 87000 | 96000 | 99000 | 55500 | 54500 | varied | Green means validated
|  | Total in k€ for personnel (without overhead) | 8751039.6667 | 1437916.6667 | 1428250 | 1408000 | 1485000 | 1170125 | 1335250 | 486498
|  | Total in K€ for personal (with +25% overheads) | 10938799.5833 | 1797395.8333 | 1785312.5 | 1760000 | 1856250 | 1462656.25 | 1669062.5 | 608122.5
|  | Travel cost | 484910 | 58905 | 58905 | 80905 | 58905 | 94105 | 108185 | 25000
|  | Purchases (allowing overheads) | 329800 | 124800 | 15000 | 22500 | 23500 | 68500 | 72500 | 3000
|  | Purchases NOT allowing overheads (subcontracting) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Total in k€ (+25% overhead, without non-funded partners) | 11957187.0833 | 2027027.0833 | 1877693.75 | 1889256.25 | 1959256.25 | 1665912.5 | 1894918.75 | 643122.5 | All partners expenditure up to (12M - EGI allowance)/6 = 1876k
|  | in % of total project | 100 | 16.9524 | 15.7035 | 15.8002 | 16.3856 | 13.9323 | 15.8475 | 5.3785
|  | Money left (up to 12m): (in kEUR) | 42812.9167
|  | Max number of Person Months per partner |  | 187.8417 | 198.6665 | 176.354 | 173.5554 | 292.2448 | 293.6261
Cost Breakdown
|  | Staff Costs | 10938799.5833
|  | Purchases | 412250
|  | Travel | 606137.5
Effort Breakdown
|  | WP1 Management | 4.621%
|  | WP2 Data Policy and Stewardship | 5.487%
|  | WP3 Data Catalog Services | 21.01%
|  | WP4 Data Analysis Services | 22.31%
|  | WP5 Virtual Neutron and X-ray Laboratory | 15.81%
|  | WP6 EOSC Integration | 13.86%
|  | WP7 Sustainibility | 4.043%
|  | Staff training in data stewardship | 7.798%
|  | WP9 Outreach &Communication | 5.054%

## EGI budget
85 | Duration [PY1-PY2] | Effort Distribution (PM) | TOT Effort (PMs) | Partner | PM Rate (euro) | (A) DIrect Personal Cost (Euro) | (B) Other direct cost (equipment, travel) | (C) Direct cost of subcontracting | (D) Indirect cost (=0.25* (A+B)) | Total estimated eligible costs (A+B+C+D) | Reimbursement rate
Cloud Compute | Special server (64 cores / 1 TB Ram) = 1000 Hours (for 1st Y) + 2000 H (2nd Y) + 4000 H (3rdY) + 10000 H (4th Y) ARCHIVING: 300 TB of tapes for open data backup | PY1-PY4 with capacity doubling every year | 24 | CESNET (Standard server only) | 4200 | 100800 | 0 | 0 | 25200 | 126000 |  | 378000
Cloud Compute | Standard server (16 cores/128 GB Ram) = 20000 Hours (for 1st Y) + 40000 H (2nd Y) + 100000 H (3rdY) + 200000 H (4th Y) ONLINE STORAGE: 50 TB ARCHIVING: 200 TB (can be increased, extra capacity needs to be invoiced) | PY1-PY4 with capacity doubling every year | 28 | DESY (special server only) | 7200 | 201600 | 0 | 0 | 50400 | 252000
Notebooks and Applications on Demand | Deployment and operation of Jupyter notebook service for PaNoSC community integrated with federated authentication, persistent storage for user notebooks, and access to PaNoSC datasets. | P1-P4 | 6 | EGI F | 7259 | 43554 | 0 | 0 | 10888.5 | 54442.5
Data transfer/FTS3 | . Alpha testing (YEAR 1): requirements analysis, piloting, porting of existing applications to FTS3, FTS3 operations: 4 PMs/YEAR 1. . Beta testing (YEAR 2,3,4): FTS3 operations in production, support to users and service providers: 1 PM from YEAR 2 till the end of the project | PY1: 4 PM PY2-3-4: 1 PM | 24 | STFC | 5856 | 140544 | 0 | 0 | 35136 | 175680
Archiving
TOTAL |  |  | 82 |  |  | 486498 | 25000 |  | 6250 | 639372.5
486498
71194.8293
|  |  |  | min | 50400
|  |  |  | max | 87108

## Budget Travel
Travel type | Travel cost | Daily Accommodation | Daily Subsistence | Avg. number of nights | Total pp | Persons per partner | Total per trip | Trips per year | Partner Annual Total | Partner total | Partner total | Notes
Between partners | 330 | 110 | 55 | 2 | 715 | 5 | 3575 | 1 | 3575 | 14300 | 14300 | all partners inc. EGI | Calculation from OpenDreamKit for a site with 1 PI and 1 FTE
Within partner sites | 220 | 82.5 | 55 | 2 | 550 | 8 | 4400 | 2 | 8800 | 35200 | 35200 | Only for ELI and CERIC | Calculation from OpenDreamKit
All partners to Brussels | 330 | 165 | 55 | 2 | 825 | 5 | 4125 | 0.25 | 1031.25 | 4125 | 4125 | all partners inc. EGI |  |  | cost | FTE | PI | site | total per year
Annual conference Hosting | N/A | N/A | N/A | N/A | N/A | N/A | 0 | 1 | 0 | 0 | 0 | Moved to Purchases |  | Duration |  | per year | per year | per year
WP1 trips between partners | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | Only ESRF, not needed | Project meetings | 2 day | 400 | 2 | 2 |  | 1600
WP2 trips between partners | 330 | 82.5 | 55 | 3 | 797.5 | 2 | 1595 | 0.5 | 797.5 | 3190 | 3190 | all partners except EGI | conference Europe | 5 day | 1200 | 2 | 1 |  | 3600
WP3 trips between partners | 330 | 82.5 | 55 | 3 | 797.5 | 2 | 1595 | 0.5 | 797.5 | 3190 | 3190 | all partners except EGI | conference international | 5 day | 2250 | 1 | 1 |  | 4500
WP4 trips between partners | 330 | 82.5 | 55 | 3 | 797.5 | 2 | 1595 | 1 | 1595 | 6380 | 6380 | all partners except EGI | project partner visit and coding sprints | 5 day | 750 | 4 | 4 |  | 6000
WP5 trips between partners | 330 | 82.5 | 55 | 3 | 797.5 | 2 | 1595 | 0.5 | 797.5 | 3190 | 3190 | all partners except EGI | hosting international visitors |  | 2000 |  |  | 1 | 2000
WP6 trips between partners | 330 | 82.5 | 55 | 3 | 797.5 | 2 | 1595 | 0.5 | 797.5 | 3190 | 3190 | all partners inc. EGI
WP7 trips between partners | 330 | 82.5 | 55 | 3 | 797.5 | 2 | 1595 | 0.5 | 797.5 | 3190 | 3190 | all partners except EGI | [5 empty] | total per year | 17700
WP8 trips between partners | 330 | 82.5 | 55 | 3 | 797.5 | 2 | 1595 | 0.5 | 797.5 | 3190 | 3190 | all partners except EGI | [5 empty] | total over 4 years | 70800
WP9 travel for outreach | 330 | 110 | 55 | 3 | 880 | 2 | 1760 | 2 | 3520 | 14080 | 14080 | Only CERIC
European conference | 330 | 165 | 55 | 5 | 1485 | 2 | 2970 | 0.5 | 1485 | 5940 | 5940 | all partners except EGI
Overseas conference | 1100 | 165 | 55 | 5 | 2255 | 2 | 4510 | 0.5 | 2255 | 9020 | 9020 | all partners except EGI
Inviting/visiting Jupyter team (Oslo/Berkeley) | [8 empty] | 5500 | 22000 | 22000 | XFEL
- registration cost? (EOSCPilot meeting was only 100EUR, but it all accumulates)
- Registration cost for conferences considered in Purchases tab
Partners | Logic |  |  |  |  | Travel budget
ESRF | Travels between partners + WP trips |  |  |  |  | 58905 | 16.25 | Persons traveling per year
ILL | Travels between partners + WP trips |  |  |  |  | 58905 | 16.25 | Persons traveling per year
XFEL | Travels between partners + WP trips + inviting Jupyter team |  |  |  |  | 80905 | 16.25 | Persons traveling per year
ESS | Travels between partners + WP trips |  |  |  |  | 58905 | 16.25 | Persons traveling per year
ELI | Travels between partners + WP trips + within partner sites |  |  |  |  | 94105 | 32.25 | Persons traveling per year
CERIC | Travels between partners + WP trips + within partner sites + WP9 |  |  |  |  | 108185 | 36.25 | Persons traveling per year
EGI | Travel to participate in WP6 |  |  |  |  | 25000
TOTAL | [5 empty] | 484910 | 4.041% | of total budget
With overheads around 5%
for psicollogycal reasons lets try to be under half million

## Purchases
|  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7
Work Package | Purchase Name | Total | ESRF | ILL | XFEL | ESS | ELI | CERIC | EGI | Overheads possible?
1 | Project Management tool | Total: 0; ESRF: 0 | Y | ESRF will provide Jira to all partners for free
9 | Public site | Total: 30000; CERIC: 30000 | Y | Roberto broke down the figure as (Visual Identity 7k; Website 17k; Hosting and Support 6k)
6 | Cloud Tools & Services | Total: 100000; ESRF: 100000; EGI: 0 | Y
1 | CFS (Certificate Financial Statement) | 24800 | 1300 | 1500 | 4000 | 5000 | 5000 | 5000 | 3000 | Y | Green means validated
9 | Coms and promotional materials | Total: 24000; CERIC: 24000 | Y
8 | Training materials (e.g videos) | Total: 50000; ELI: 50000 | Y
1 | Annual conference not travel items | Total: 20000; ESRF: 10000; XFEL: 5000; ESS: 5000 | Y | Volunteers needed to take on 3k. For the time being assigned to XFEL and ESS and subject to approval
All | Conference fees | 36000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 |  | Y
All | Workshop organisation | 24000 | 4000 | 4000 | 4000 | 4000 | 4000 | 4000 |  | Y
9 | Open access publications | 21000 | 3500 | 3500 | 3500 | 3500 | 3500 | 3500 |  | Y
| Total (items allowing overheads) | 329800 | 124800 | 15000 | 22500 | 23500 | 68500 | 72500 | 3000
| Total (items NOT allowing overheads) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| TOTAL | 329800 | 124800 | 15000 | 22500 | 23500 | 68500 | 72500 | 3000
No overheads allowed for subcontracting
PLEASE NOTE: Column K explains for which items overheads (+25%) will be added in the main PaNOSC budget sheet

## Cloud services
Partner | Service | Machine Name | vCPUs | Memory (GBs) | Storage (GBs) | Simultaneous users | Price per hour | Hours per job | Cost per job | Price per day | Price per year | Price per 4 years | Reserved price | spot | total project
ESRF | Jupyter | r4.4xlarge | 16 | 122 |  | 20 | 1.0109 |  |  | 24.2611 | 8855.3088 | 35421.2352 |  |  | 0
ILL | Xrystal | r4.4xlarge | 2 | 128 |  | 1 | 1.0109 | 100 | 101.088 | 24.2611 | 8855.3088 | 35421.2352 |  |  | 93000.96
ESRF | Ptycho | x1.16xlarge | 64 | 976 |  | 1 | 5.6449 | 24 | 135.4774 | 135.4774 | 49449.2364 | 197796.9456 |  |  | 124639.1712
XFEL.EU | Ptycho (as ESRF) | x1.16xlarge | 64 | 976 | 0 | 1 | 5.6449 | 24 | 135.4774 | 135.4774 | 49449.2364 | 197796.9456 |  |  | 124639.1712
XFEL.EU | Jupyter (as ESRF) | r4.4xlarge | 16 | 122 | 0 | 20 | 1.0109 | 0 | 0 | 24.2611 | 8855.3088 | 35421.2352 |  |  | 0
XFEL.EU | SIMEX/WPG | x1.16xlarge | 64 | 976 |  | 0.125 | 5.6449 | 3 | 16.9347 | 16.9347 | 6181.1546 | 24724.6182 |  |  | 15579.8964
XFEL.EU | SIMEX/MD | p3.16xlarge | 64 | 488 | 0 | 0.07 | 24.48 | 24 | 587.52 | 41.1264 | 15011.136 | 60044.544 |  |  | 540518.4
CERIC | Ptycho | r4.4xlarge | 16 | 122 |  | 1 | 5.6449 | 24 | 135.4774 | 135.4774 | 49449.2364 | 197796.9456 |  |  | 124639.1712
CERIC | Jupyter | x1.16xlarge | 64 | 976 |  | 20 | 1.0109 |  |  | 24.2611 | 8855.3088 | 35421.2352 |  |  | 0
ESS | SIMEX/DFT (WP5) | 2 x c5.18xlarge | 144 | 288 |  | 0.5 | 5.6692 |  |  | 68.0298 | 24830.8858 | 99323.543 |  |  | 0
ESS | SIMEX/Spinw (WP5) | c5.9xlarge | 36 | 72 | 0 | 0.5 | 1.4173 |  | 0 | 17.0075 | 6207.7214 | 24830.8858 |  |  | 0
ESS | SIMEX/McStas (WP5) | c5.18xlarge | 72 | 144 |  | 1 | 2.8346 |  |  | 68.0298 | 24830.8858 | 99323.543 |  |  | 0
ESS | WP4 (sans, refl, qens, powder) | p3.2xlarge | 8 | 61 |  | 20 | 2.5092
ESS | WP4 (ins, sxtal, img) | r4.4xlarge | [12 empty] | 1023016.77
|  |  | EUR/vCPU/h | EUR/Gb/h
|  | c5 | 0.039369 | 0.019685
|  | p3 | 0.3825 | 0.050164
|  | x1 | 0.088201 | 0.0010357 |  |  | Y1
|  | r4 | 0.06318 | 0.0082859 |  | 1.01 | 20200 | 40400 | 101000 | 202000 | 363600
[6 empty] | 5.64 | 5640 | 11280 | 22560 | 56400 | 95880
Note on B15: This will be many small jobs. The service will just be more like a web-service that needs load-balancing. Some of the software can use gpu power.

## WP partners
WP | Title | Lead | Co-Lead | Leader | Co-Leader
1 | Management | ESRF |  | Jordi (ESRF)
2 | Data Policy and Stewardship | ESRF | ESS | Andy (ESRF)
3 | Data Catalog Services | ESS | CERIC | Tobias *ESS)
4 | Data Analysis Services | XFEL | ILL | Hans (XFEL)
5 | Data Modelling and Simulation | XFEL |  | Carsten (XFEL)
6 | EOSC Integration | ILL | EGI | Jean Francois (ILL)
7 | Sustainibility | CERIC |  | Roberto (CERIC)
8 | User Training | ESS | ELI | Thomas (ESS) | Tamas (ELI)
9 | Outreach and Communication | CERIC |  | Nicoleta (CERIC)

## PaNDaaS budget
PaNDaaS work package matrix (in p-month)
| Part. # |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21
WP | Task title |  | ESRF | ALBA | CYI | DESY | DLS | ELI-ALPS | ELETTRA | ENTROUV | ESS | EXACT | E-XFEL | HZB | ILL | KIT | MAX-IV | PSI | SESAME | SLAC | SOLEIL | SNS | STFC
Partner description
Commitment Letter | bar: 2 to 7; 9 to 17; 19; 21
1 - Management |  | Total WP
T1 | Project Management | 48 | 1: 48
T2 | Com & Interaction Commission | 2 | 1: 2
T3 | Mgt. Internal Communication | 2 | 1: 2
T4 | Mgt. Meetings | 2 | 1: 2
T5 | Mgt. Project Reporting | 2 | 1: 2
| Sub-total | 56 | 1: 56
2- Dis & Outreach
T1 | Overall Coordination | 13.5 | 3.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
T2 | Public Web Site | 1 | bar: 1
T3 | Scientific Articles, dissemination material | 2 | 1: 2
T4 | Participation in events | 1 | bar: 1
T5 | Organisation topical workshops | 10 | 1: 1.5; 2: 1.5; 4: 1.5; 7: 1.5; 16: 1.5; 17: 1.5; 21: 1.5
T6 | Establish links | 1 | bar: 1
T7 | Articles in periodic newsletters | 3 | 1: 3
T8 | Production of posters | 1 | bar: 1
| Sub-total | 33 | 14 | 2 | 0.5 | 2 | 0.5 | 0.5 | 2 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 2 | 2 | 0.5 | 0.5 | 0.5 | 2
3 - Health & LS UCs
T1 | Select softw. for Structural Biology | 12 | 5: 6; 12: 6
T2 | Select softw. for Serial Crystallography | 6 | 1: 6
T3 | Select softw. for optimised phase contrast imaging | 6 | 4: 6
T4 | Select softw. for BioSAXS (Molecular Dynamics) | 6 | 19: 6
T5 | Select softw. for Cellular Soft X-Rays | 6 | 2: 6
T6 | Select softw. for 2D crystal FEL diffraction analysis | 6 | 11: 6
T7 | Select softw. for XFEL CrystFEL | 6 | 11: 6
T8 | Service & Service Verification 1 | 21 | 1: 3; 2: 3; 4: 3; 5: 3; 11: 3; 12: 3; 19: 3
T9 | Service & Service Verification 2 | 21 | 1: 3; 2: 3; 4: 3; 5: 3; 11: 3; 12: 3; 19: 3
T10 | Service & Service Verification 3 | 21 | 1: 3; 2: 3; 4: 3; 5: 3; 11: 3; 12: 3; 19: 3
T11 | Service & Service Verification 4 | 21 | 1: 3; 2: 3; 4: 3; 5: 3; 11: 3; 12: 3; 19: 3
| Sub-total | 132 | 1: 18; 2: 18; 4: 18; 5: 18; 11: 24; 12: 18; 19: 18
4 - Materials Science UCs
T1 | Select softw. for Single cryst. neutron scat | 6 | 13: 6
T2 | Select softw. for absorption and emission spectrocopy | 6 | 16: 6
T3 | Select softw. for resonant diffraction pump-probe data | 6 | 7: 6
T4 | Select softw. for gisaxs | 6 | 4: 6
T5 | Select softw. for SANS and SAXS | 6 | 9: 6
T6 | Select softw. for spectroscopy | 8 | 4: 2; 15: 6
T7 | Service & Service Verification 1 | 21 | 4: 3; 7: 3; 9: 3; 13: 3; 15: 3; 16: 3; 17: 3
T8 | Service & Service Verification 2 | 21 | 4: 3; 7: 3; 9: 3; 13: 3; 15: 3; 16: 3; 17: 3
T9 | Service & Service Verification 3 | 21 | 4: 3; 7: 3; 9: 3; 13: 3; 15: 3; 16: 3; 17: 3
T10 | Service & Service Verification 4 | 21 | 4: 3; 7: 3; 9: 3; 13: 3; 15: 3; 16: 3; 17: 3
| Sub-total | 122 | 4: 20; 7: 18; 9: 18; 13: 18; 15: 18; 16: 18; 17: 12
5 - Industrial UCs
T1 | Select softw. for Nanoelectronics | 6 | 1: 6
T2 | Select softw. for Nanotomography | 6 | 1: 6
T3 | Select softw. for Catalysis | 6 | 5: 6
T4 | Select softw. for pharmaceuticals | 6 | 2: 6
T5 | Select softw. for neutron protein crystallography | 6 | 9: 6
T6 | Select softw. For strain-stress automatic proc. | 12 | 1: 6; 2: 6
T7 | Select softw. for Nuclear and particle physics | 6 | 13: 6
T8 | Select softw for quantum magnetism + fields | 6 | 21: 6
T9 | Service & Service Verification 1 | 18 | 1: 3; 2: 3; 5: 3; 9: 3; 13: 3; 21: 3
T10 | Service & Service Verification 2 | 18 | 1: 3; 2: 3; 5: 3; 9: 3; 13: 3; 21: 3
T11 | Service & Service Verification 3 | 18 | 1: 3; 2: 3; 5: 3; 9: 3; 13: 3; 21: 3
T12 | Service & Service Verification 4 | 18 | 1: 3; 2: 3; 5: 3; 9: 3; 13: 3; 21: 3
| Sub-total | 126 | 1: 30; 2: 24; 5: 18; 9: 18; 13: 18; 21: 18
6 - Architecture and Ref Impl.
T1 | Define minimum set of functionalities | 18 | 1: 2; 3: 1; 4: 2; 6: 3; 8: 1; 12: 2; 13: 4; 21: 3
T2 | Select cloud platform | 24 | 1: 6; 3: 3; 4: 2; 6: 3; 10: 1; 12: 2; 13: 3; 14: 2; 21: 2
T3 | Review and select hybrid cloud API layers | 21 | 1: 3; 3: 4; 4: 2; 8: 1; 13: 4; 15: 3; 21: 4
T4 | Edit technical reference implementation manual | 8 | 3: 5; 13: 1; 15: 2
T5 | Implement basic architecture in all RIs | 78 | 3 | 3 | 3 | 3 | 3 | 3 | 3 |  | 3 | 27 | 3 | 3 | 3 | 3 | 3 | 3 | 3 |  | 3 |  | 3
T6 | Development User access web portal | 47 | 2: 12; 6: 6; 8: 1; 12: 4; 13: 14; 21: 10
T7 | Evaluate and implement Remote Desktop solution | 19 | 1: 5; 4: 6; 12: 6; 13: 2
T8 | Common Monitoring and accounting tools | 16 | 1: 4; 13: 8; 21: 4
T9 | System Image configuration, deployment | 33 | 3: 5; 10: 16; 12: 6; 13: 3; 21: 3
| Sub-total | 264 | 23 | 15 | 21 | 15 | 3 | 15 | 3 | 3 | 3 | 44 | 3 | 23 | 42 | 5 | 8 | 3 | 3 |  | 3 |  | 29
7 - Common Tools
T1 | Enabling access with Umbrella ID | 62 | 4: 3; 5: 6; 8: 28; 13: 12; 15: 3; 16: 10
T2 | LOA & Authorisation | 24 | 5: 6; 8: 12; 13: 6
T3 | Service catalogue | 26 | 3: 6; 6: 5; 13: 3; 21: 12
T4 | Data movement service | 51 | 3: 4; 4: 12; 6: 5; 7: 12; 13: 6; 15: 12
T5 | Other cloud infrastructures | 22 | 3: 4; 4: 6; 21: 12
T6 | Cloud security | 24 | 8: 12; 13: 6; 21: 6
| Sub-total | 209 | 3: 14; 4: 21; 5: 12; 6: 10; 7: 12; 8: 52; 13: 33; 15: 15; 16: 10; 21: 30
8 - Online
T1 | Data streaming architecture | 82 | 1: 6; 4: 10; 6: 20; 16: 46
T2 | Optimized reduction/analysis algorithms | 46 | 3: 12; 4: 18; 6: 10; 16: 6
T3 | Workflow control and configuration | 48 | 5: 6; 6: 6; 9: 12; 13: 12; 16: 6; 19: 6
T4 | External tools integration | 42 | 1: 6; 2: 6; 7: 12; 13: 6; 16: 6; 21: 6
| Sub-total | 218 | 1: 12; 2: 6; 3: 12; 4: 28; 5: 6; 6: 36; 7: 12; 9: 12; 13: 18; 16: 64; 19: 6; 21: 6
9 - Data Access and Visualisation and Workflow
T1 | Data access | 67 | 1: 12; 2: 8; 5: 20; 13: 6; 15: 12; 17: 3; 21: 6
T2 | Data browsers | 35 | 1: 6; 2: 8; 5: 6; 7: 6; 17: 3; 21: 6
T3 | Data caching | 20 | 5: 2; 6: 12; 14: 6
T4 | Volume rendering | 38 | 2: 8; 6: 12; 14: 18
T5 | Analysis workflows | 60 | 1: 18; 5: 6; 11: 18; 19: 12; 21: 6
T6 | Workflow preservation | 52 | 5: 6; 11: 10; 13: 12; 19: 12; 21: 12
| Sub-total | 272 | 36 | 24 |  |  | 40 | 24 | 6 |  |  |  | 28 |  | 18 | 24 | 12 | 0 | 6 |  | 24 |  | 30
10 - User support tools & training
T1 | Community portal | 11 | 3: 3; 17: 8
T2 | Coordinate and edit technical documentation | 8 | 3: 5; 4: 3
T3 | User training | 10 | 3: 5; 17: 5
T4 | Programmer training | 28 | 3: 5; 14: 18; 17: 5
T5 | Setup and run helpdesk | 29 | 3: 24; 4: 3; 17: 2
| Sub-total | 86 | 3: 42; 4: 6; 14: 18; 17: 20
11 - Business Model & Sustainab.
T1 | Data management plan | 4 | bar: 1 to 4
T2 | Market analysis and segmentation | 4 | 2: 2; 12: 1; 15: 1
T3 | Financial plans, cloud and data preservation | 8 | 1: 1; 2: 1; 12: 1; 13: 4; 21: 1
T4 | Service management/strategy/design | 8 | 2: 4; 15: 4
T5 | Externalise | 4 | 19: 2; 21: 2
T6 | Federation | 7 | 1: 2; 2: 2; 7: 2; 13: 1
| Sub-total | 35 | 1: 4; 2: 10; 3: 1; 4: 1; 7: 2; 12: 2; 13: 5; 15: 5; 19: 2; 21: 3
| PM Total WPs | 1553 | 193 | 99 | 90.5 | 111 | 97.5 | 85.5 | 55 | 55.5 | 51.5 | 44.5 | 55.5 | 43.5 | 152.5 | 47.5 | 58.5 | 97 | 43 | 0.5 | 53.5 | 0.5 | 118
| PY Total WPs | 129.4167 | 16.0833 | 8.25 | 7.5417 | 9.25 | 8.125 | 7.125 | 4.5833 | 4.625 | 4.2917 | 3.7083 | 4.625 | 3.625 | 12.7083 | 3.9583 | 4.875 | 8.0833 | 3.5833 | 0.041667 | 4.4583 | 0.041667 | 9.8333
| Average yearly staff cost |  | 85 | 69 | 55 | 79 | 76 | 70 | 75 | 90 | 90 | 50 | 79 | 84 | 85 | 83 | 90 | 96 | 35 | 80 | 75 | 80 | 85
| Total in k€ (without overhead) | 10125.4583 | 1367.0833 | 569.25 | 414.7917 | 730.75 | 617.5 | 498.75 | 343.75 | 416.25 | 386.25 | 185.4167 | 365.375 | 304.5 | 1080.2083 | 328.5417 | 438.75 | 776 | 125.4167 | 3.3333 | 334.375 | 3.3333 | 835.8333
| Travel cost | 666 | 36 | 27 | 45 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 45 | 54 | 27 | 54 | 27
| Total in k€ (+25% overhead, without non-funded partners) | 12342.2396 | 1753.8542 | 745.3125 | 574.7396 | 947.1875 | 805.625 | 657.1875 | 463.4375 | 554.0625 | 516.5625 | 265.5208 | 490.4688 | 414.375 | 1384.0104 | 444.4271 | 582.1875 | 0 | 213.0208 | 0 | 451.7188 | 0 | 1078.5417
| in % of total funded | 100 | 14.2102 | 6.0387 | 4.6567 | 7.6744 | 6.5274 | 5.3247 | 3.7549 | 4.4892 | 4.1853 | 2.1513 | 3.9739 | 3.3574 | 11.2136 | 3.6009 | 4.717 | 0 | 1.7259 | 0 | 3.6599 | 0 | 8.7386
| in % of total project | 100 | 13.5014 | 5.622 | 4.0965 | 7.217 | 6.0985 | 4.9257 | 3.3949 | 4.1109 | 3.8146 | 1.8312 | 3.6085 | 3.0073 | 10.6682 | 3.2447 | 4.3331 | 7.6639 | 1.2386 | 0.03292 | 3.3023 | 0.03292 | 8.2548
| Subcontracting/PSI Swiss funding/USA |  | 1: 104; 16: 1003.75; 18: 57.3333; 20: 57.3333
Travel cost reasoning: | I average trip = 600€. 3*5 for annual meetings, 3x10 trips for WP coordination = 45 * 600 = 27k€ for a standard partner
ESRF + 15 trips for coordination activities = 24k€
CYI + SESAME = 1000 € per trip = 45k€
| Management + Policies | 91
| Outreach + Dissemination | 33
| Data analysis services | 380
| Research and technical development | 1049
1553

## Gantt
[5 empty] | Year 1 | [11 empty] | Year 2 | [11 empty] | Year 3 | [11 empty] | Year 4
Work Package | Id | Task Name | Start | End | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48
WP1 Management | D1.1 | Project initiation Documentation | 1 | 2
| D1.2 | Mid-Year summary | 1 | 48
| D1.3 | Annual workshop report
| D1.4 | Data management plan | 1 | 48
WP2 Data Policy and Stewardship | D2.1 | PaNOSC data policy framework updated | 1 | 6
| D2.2 | TMP Template published | 6 | 18
| D2.3 | Guidelines published | 9 | 36
| D2.4 | Integration of the policy in the User Access & Facility information systems | 1 | 24
WP3 Data Catalog Services | D3.1 | API Definition | 1 | 28
| D3.2 | Demonstrator implementation | 8 | 20
| D3.3 | Catalog service | 20 | 44
| D3.4 | Implementation report from facilities | 12 | 48
| D3.5 | NeXus Metadata Mapping Schema and proposed new Definitions | 1 | 42
WP4 Data Analysis Services | D4.1 | Report data analysis capture | 1 | 12
| D4.2 | Prototype remote desktop and Jupyter service | 1 | 36
| D4.3 | Remote desktop and Jupyter analysis service tested at EOSC | 13 | 48
| D4.4 | Jupyter based analysis services | 1 | 48
WP5 Virtual Neutron and X-ray Laboratory | D5.1 | Prototype simulation data formats | 1 | 48
| D5.2 | Documented simulation APIs | 1 | 24
| D5.3 | Documented simulation tasks executable | 13 | 36
| T5.4 | Software tested & released including interactive simulation & analysis workflow | 25 | 48
WP6 EOSC Integration | D6.1 | DataHub: EGI DataHub integration with the facilities data repositories | 1 | 48
| D6.2 | Compute cloud: integration of local compute resources into the EOSC cloud | 1 | 48
| D6.3 | AAI: Integration of the PaN AAI into the EOSC | 1 | 48
| D6.4 | Software catalogue: Demonstration of the PaN software catalogue integration into EOSC | 1 | 36
| D6.5 | Report on EOSC integration | 12 | 48
WP7 Sustainibility | D7.1 | Photon and Neutron EOSC Stakeholder Feedback | 1 | 48
| D7.2 | Photon and Neutron EOSC metrics and costs model | 9 | 36
| D7.3 | Photon and Neutron EOSC Business model reference document | 13 | 42
| D7.4 | Photon and Neutron EOSC Sustainability plan | 19 | 48
Staff training in data stewardship | D8.1 | Report on lessons learned and future prospects for adopting best practises data stewardship at the PaNOSC facilities | 4 | 15
| D8.2 | Report on lessons learned for adopting the e-learning platform at the PaNOSC facilities, task 8.4 | 19 | 30
| D8.3 | Teaching material accessible in the e-learning platform at panlearning.org, task 8.5-7 | 25 | 36
| D8.4 | Closing report including report from summer school, task 8.8 | 13 | 42
WP9 Outreach &Communication | D9.1 | PaNOSC’s Communication and Dissemination Plan | 1 | 48
| D9.2 | PaNOSC’s Website | 13 | 48
| D9.3 | PaNOSC’s repository for internal communication
| D9.4 | Dissemination and Outreach activities | 1 | 48
[5 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48
[5 empty] | Year 1 | [11 empty] | Year 2 | [11 empty] | Year 3 | [11 empty] | Year 4
D1.1
D1.2
D1.2
D1.2
D2.1
D7.1
D7.3
D7.4
D2.4
D3.1
D3.5
D4.1
D5.2
D5.1
D6.1
D8.1
D8.3
D9.1
D1.2
D1.3
D1.3
D1.3
D1.3
D1.4
D2.2
D2.3
D3.2
D3.3
D3.4
D4.2
D4.3
D4.4
D5.3
D5.4
D6.2
D6.3
D6.4
D6.5
D7.2
D8.2
D8.4
D9.2
D9.3
D9.3